## WC 18.03 Programme of works
Roadwork Identifier | Road | Road/Direction | Affected Routes | Traffic Management Types/Contractor | Works Activity Type/Contractor | Start Date | End Date | Week Start | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | No. of Activities | Roadwork Identifier Lookup
SW/2024/43669 | A701 | A701 Bloomfield rbt SB- lane closure Direction: S | SRWR: 3542522 Location: A701 Bloomfield rbt SB- lane closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43669 18/03/2024
SW/2024/42449 | A725 | A725 N/B East Kilbride Expressway A724 to Whisteberry N/S Lane Direction: E | SRWR: 3460212 Location: A725 N/B East Kilbride Expressway A724 to Whisteberry N/S Lane Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - HBS | Barrier Repair - HBS (Primary) | 2024-02-07 20:00 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 9 | SW/2024/42449 18/03/2024
SW/2024/42450 | A725 | A725 NB Onslip from A724 Glasgow Road - Closure Direction: E | SRWR: 3460197 TRO 3511571 Location: A725 NB Onslip from A724 Glasgow Road - Closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: Traffic wishing to join the A725 at Glasgow Road (A7624 onslip) will be directed south on A724 Glasgow Road, taking the second exit onto B7012 Whistleberry Road turning left onto A725 E\B Whistleberry onslip where the diversion ends. | Road Closure (No Speed Restriction) - HBS | Barrier Repair - HBS (Primary) | 2024-02-07 20:00 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 9 | SW/2024/42450 18/03/2024
SW/2024/42451 | A725 | A725 NB Whistleberry Offslip- Closure Direction: E | SRWR: 3460212 TRO 3511605 Location: A725 NB Whistleberry Offslip- Closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: A737 E/B traffic wishing to exit at Whistleberry offslip will continue eastbound to Bellshill roundabout where they will be directed around the roundabout to head W/B on the A725 and continue to W/B Whistleberry offslip with the diversion ending onto B7012 Whistleberry Road. | Road Closure (No Speed Restriction) - HBS | Barrier Repair - HBS (Primary) | 2024-02-07 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 9 | SW/2024/42451 18/03/2024
SW/2024/43266 | A725 | A725 EB Righead Rbt @ Underpass - No Obstruction on CW/FP Direction: E | SRWR: 3527588 Location: A725 EB Righead Rbt @ Underpass - No Obstruction on CW/FP Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - SGN | Utility Works - SGN (Primary) | 2024-02-19 13:00 | 2024-03-18 18:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/43266 18/03/2024
SW/2024/43405 | A725 | A725 EB Offslip to B7012 - Slip Closure Direction: E | SRWR: 3532046 Location: A725 EB Offslip to B7012 - Slip Closure Direction: E Delay: Slight Delay/At All Times Diversion: For traffic travelling East on the A725 continue East to Douglas Street Off ramp and follow signage. | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - South Lanarkshire Council (Primary) | 2024-03-18 04:00 | 2024-03-22 21:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43405 18/03/2024
SW/2024/43877 | A725 | A725 Whirlies Bypass WB H/S Closure Direction: W | SRWR: 3542567 Location: A725 Whirlies Bypass WB H/S Closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Apex Traffic Management | Barrier Repair - W & I Gilbert (Primary) | 2024-03-21 09:30 | 2024-03-26 15:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/43877 18/03/2024
SW/2024/43943 | A725 | A725 Whirlies Bypass OB EB - H/S Closure Direction: E | SRWR: 3542616 Location: A725 Whirlies Bypass OB EB - H/S Closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Apex Traffic Management | Barrier Repair - W & I Gilbert (Primary) | 2024-03-21 09:30 | 2024-03-26 15:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/43943 18/03/2024
SW/2024/42858 | A726 | A726 E/B Righead Rbt to Birniehill rbt - Progressive N/S lane closure Direction: E | SRWR: 3438199 Location: A726 E/B Righead Rbt to Birniehill rbt - Progressive N/S lane closure Direction: E Delay: Little or No Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Footway Works - Hillhouse (Primary) | 2024-02-26 09:30 | 2024-03-29 15:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/42858 18/03/2024
SW/2024/42859 | A726 | A726 E/B Righead Rbt to Birniehill rbt - verge works Direction: E | SRWR: 3438199 Location: A726 E/B Righead Rbt to Birniehill rbt - verge works Direction: E Delay: Little or No Delay/At All Times Diversion: No Diversion | Works Entirely on Footway (No Speed Restriction) - Amey | Footway Works - Hillhouse (Primary) | 2024-02-26 | 2024-03-22 15:30 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/42859 18/03/2024
SW/2023/37065 | A737 | A737 WB Clerksbridge Rbt to Kilwinning - Stop & Go Direction: W | SRWR: Short Duration Progressive Stop & Go Location: A737 WB Clerksbridge Rbt to Kilwinning - Stop & Go Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2023-02-10 09:30 | 2024-04-12 15:30 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2023/37065 18/03/2024
SW/2023/37066 | A737 | A737 EB Kilwinning to Clerksbridge Rbt Stop & Go Direction: E | SRWR: Short Duration Progressive Stop & Go Location: A737 EB Kilwinning to Clerksbridge Rbt Stop & Go Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2023-02-10 09:30 | 2024-04-12 15:30 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2023/37066 18/03/2024
SW/2024/43504 | A737 | A737 Linclive IC Linwood NB - Lane Closure Direction: N | SRWR: 3536793 Location: A737 Linclive IC Linwood NB - Lane Closure Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/43504 18/03/2024
SW/2024/43549 | A737 | A737 SB Linwood to Johnstone Closure Direction: S | SRWR: 3511946 3511955 TRO 3536599 Location: A737 SB Linwood to Johnstone Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: A737 SB traffic shall exit at Linwood SB offslip, take the third exit onto A761, take the first exit at the next 2 roundabouts continuing on the A761 Bridge of Weir Rd , then the first exit at Deafhillock roundabout onto B789 Barrochan Road turning right onto A737 SB Johnston on-slip. | Road Closure (No Speed Restriction) - Apex Traffic Management | Sign Installation/Repairs - Clearview Intelligence (Primary) | 2024-03-24 20:00 | 2024-03-27 06:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43549 18/03/2024
SW/2024/43550 | A737 | A737 SB Linwood Onslip Closure Direction: S | SRWR: 3511946 TRO 353599 Location: A737 SB Linwood Onslip Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: Traffic wishing to join A737 at Linwood will , take the next exit onto A761, take the first exit at the next 2 roundabouts continuing on the A761 Bridge of Weir Rd , then the first exit at Deafhillock roundabout onto B789 Barrochan Road turning right onto A737 W/B Johnston on-slip. | Road Closure (No Speed Restriction) - Apex Traffic Management | Sign Installation/Repairs - Clearview Intelligence (Primary) | 2024-03-24 20:00 | 2024-03-27 06:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43550 18/03/2024
SW/2024/43551 | A737 | A737 SB Johnstone Offslip Closure Direction: S | SRWR: 3511955 TRO 353599 Location: A737 SB Johnstone Offslip Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Road Closure (No Speed Restriction) - Apex Traffic Management | Sign Installation/Repairs - Clearview Intelligence (Primary) | 2024-03-24 20:00 | 2024-03-27 06:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43551 18/03/2024
SW/2024/43842 | A737 | A737 NB Barrochan IC - Lane 1 Closure Direction: N | SRWR: 3538853 Location: A737 NB Barrochan IC - Lane 1 Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Class 1 | Barrier Repair - Amey (Primary) Barrier Repair - HBS (Primary) | 2024-03-17 20:00 | 2024-03-18 06:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/43842 18/03/2024
SW/2024/43919 | A737 | A737 Roadhead - Clerksbridge Toll - SB Progressive TTL's Direction: S | SRWR: 3541057 Location: A737 Roadhead - Clerksbridge Toll - SB Progressive TTL's Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Lining Works - CTM Ltd (Primary) | 2024-03-24 20:00 | 2024-03-25 06:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43919 18/03/2024
SW/2024/43920 | A737 | A737 Clerksbridge Toll - Roadhead NB Progressive TTL's Direction: N | SRWR: 3541057 Location: A737 Clerksbridge Toll - Roadhead NB Progressive TTL's Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Lining Works - CTM Ltd (Primary) | 2024-03-24 20:00 | 2024-03-25 06:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43920 18/03/2024
SW/2024/43979 | A737 | A737 The Den WB - TTLS Direction: W | SRWR: 3541820 Location: A737 The Den WB - TTLS Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 09:30 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/43979 18/03/2024
SW/2024/43980 | A737 | A737 The Den EB - TTLS Direction: E | SRWR: 3541820 Location: A737 The Den EB - TTLS Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 09:30 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/43980 18/03/2024
SW/2024/44013 | A737 | A737 Manrahead Rbt Dalry EB - TTLS Direction: E | SRWR: 3542399 Location: A737 Manrahead Rbt Dalry EB - TTLS Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 09:30 | 2024-03-21 15:30 | 2024-03-18 |  |  |  | X |  |  |  | 1 | SW/2024/44013 18/03/2024
SW/2024/44014 | A737 | A737 Manrahead Rbt Dalry WB - TTLS Direction: W | SRWR: 3542399 Location: A737 Manrahead Rbt Dalry WB - TTLS Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 09:30 | 2024-03-21 15:30 | 2024-03-18 |  |  |  | X |  |  |  | 1 | SW/2024/44014 18/03/2024
SW/2023/41348 | A738 | A738 WB from Kilwinning to Pennyburn Rbt - Stop and Go Direction: W | SRWR: Minor short duration Location: A738 WB from Kilwinning to Pennyburn Rbt - Stop and Go Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2023-12-04 09:30 | 2024-04-12 15:30 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2023/41348 18/03/2024
SW/2023/41349 | A738 | A738 EB from Pennyburn Rbt to Kilwinning - Stop and Go Direction: E | SRWR: Minor short duration Location: A738 EB from Pennyburn Rbt to Kilwinning - Stop and Go Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2023-12-04 09:30 | 2024-04-12 15:30 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2023/41349 18/03/2024
SW/2024/43592 | A74(M) | A74(M) NB slip to A75 EB- no obstruction on c/way or footway CLOSURE Direction: N | SRWR: 3540961,3540967,3540974 Location: A74(M) NB slip to A75 EB- no obstruction on c/way or footway CLOSURE Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43592 18/03/2024
SW/2023/41037 | A75 | A75 The Old Glen - Cycle Way Closure Direction: E | SRWR: 3470712 Location: A75 The Old Glen - Cycle Way Closure Direction: E Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2023-11-09 09:30 | 2024-07-26 16:30 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/41037 18/03/2024
SW/2024/42856 | A75 | A75 from A77 Jct SB Sranraer to Newton Stewart Diverson Direction: S | SRWR: 3486523 Location: A75 from A77 Jct SB Sranraer to Newton Stewart Diverson Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Contraflow Ltd | Road Part of a Diversion Route - Network Rail (Primary) | 2024-03-16 23:00 | 2024-03-19 09:00 | 2024-03-18 | X | X | [5 empty] | 3 | SW/2024/42856 18/03/2024
SW/2024/42857 | A75 | A75 NB From Newton Stewart to A77 Jct Stranraer Diversion Direction: N | SRWR: 3486523 Location: A75 NB From Newton Stewart to A77 Jct Stranraer Diversion Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Contraflow Ltd | Road Part of a Diversion Route - Network Rail (Primary) | 2024-03-16 23:00 | 2024-03-19 09:00 | 2024-03-18 | X | X | [5 empty] | 3 | SW/2024/42857 18/03/2024
SW/2024/43593 | A75 | A75 Off Slip Gretna EB- no obstruction on c/way or footway Direction: E | SRWR: 3540995 Location: A75 Off Slip Gretna EB- no obstruction on c/way or footway Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43593 18/03/2024
SW/2024/43594 | A75 | A75 On Slip from Gretna EB- SLIP ROAD CLOSURE Direction: E | SRWR: 3541043 TRO 3541045 Location: A75 On Slip from Gretna EB- SLIP ROAD CLOSURE Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: NORTH DIVERSION; continue B7076 north- Take left at 3rd jct signed Annan/Dumfries- follow rd at jct turn right onto A75 east- end. SOUTH DIVERSION- follow B7076 south- at rbt 4th exit onto Annan Rd B721- rejoin A75 east | Road Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 19:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43594 18/03/2024
SW/2024/43595 | A75 | A75 at Gretna EB- LANE CLOSURES Direction: E | SRWR: 3541054 Location: A75 at Gretna EB- LANE CLOSURES Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 19:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43595 18/03/2024
SW/2024/43596 | A75 | A75 at Gretna WB - LANE CLOSURE Direction: W | SRWR: 3541059 Location: A75 at Gretna WB - LANE CLOSURE Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 19:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43596 18/03/2024
SW/2024/43597 | A75 | A75 Gretna bypass WB to A74 (M) Onslip Jct 22 - SLIP CLOSURE Direction: W | SRWR: 3541067,3541071 TRO 3541076 Location: A75 Gretna bypass WB to A74 (M) Onslip Jct 22 - SLIP CLOSURE Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: Leave A75 and follow rd to Glasgow rd B7076- at jct turn right onto Glasgow rd B7076- at rbt take 2nd exit B7076- follow B7076 and rejoin Motorway at M6 jct 45- end | Road Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 19:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43597 18/03/2024
SW/2024/43598 | A75 | A75 Gretna Off Slip WB- SLIP ROAD CLOSURE Direction: W | SRWR: 3541083 TRO 3541085 Location: A75 Gretna Off Slip WB- SLIP ROAD CLOSURE Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: Leave A75 and follow rd to Glasgow rd B7076- at jct turn right onto Glasgow rd B7076- END | Road Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 19:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43598 18/03/2024
SW/2024/43605 | A75 | A75 The Glen West end of Dumfries By Pass road closure Direction: W | SRWR: 3535804,TRO 3535821 Location: A75 The Glen West end of Dumfries By Pass road closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: Leave rbt at Hospital- follow national cycle route 7- at rbt take 2nd exit onto A711- at rbt take 2nd exit onto A711 to Dalbeattie- at jct turn right onto A745- at rbt take 3rd exit onto A745- rejoin A75 west- end. | Road Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 19:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43605 18/03/2024
SW/2024/43658 | A75 | A75 WB Dumfries bypass A76 to A701 link road- ROAD CLOSURE Direction: W | SRWR: 3541304 TRO 3541305 Location: A75 WB Dumfries bypass A76 to A701 link road- ROAD CLOSURE Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: at Bloomfield rbt take exit for Dumfries- continue on Edinburgh rd- at rbt take 2nd exit Edinburgh rd- at jct turn right onto Glasgow st- at rbt take 2nd exit Glasgow st- at rbt take 2nd exit Glasgow st- rejoin A75 at Cuckoo br rbt- end | Road Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-19 19:00 | 2024-03-21 06:00 | 2024-03-18 |  | X | X | X |  |  |  | 4 | SW/2024/43658 18/03/2024
SW/2024/43659 | A75 | A75 EB Dumfries bypass A76 to A701 link road - ROAD CLOSURE Direction: E | SRWR: 3541304 TRO 3541305 Location: A75 EB Dumfries bypass A76 to A701 link road - ROAD CLOSURE Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: leave cuckoo bridge rbt at 1st exit onto Glasgow st- at rbt take 2nd exit onto Glasgow st- at rbt take 2nd exit onto Glasgow st- at jct turn left 0nto A780- at rbt take 1st exit onto Edinburgh rd- rejoin A75 east at bloomfield rbt- end | Road Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-19 19:00 | 2024-03-21 06:00 | 2024-03-18 |  | X | X | X |  |  |  | 4 | SW/2024/43659 18/03/2024
SW/2024/43661 | A75 | A75 Dancingknowe rbt WB- lane closure Direction: W | SRWR: 3542457,3542468,3542480 Location: A75 Dancingknowe rbt WB- lane closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43661 18/03/2024
SW/2024/43662 | A75 | A75 Dancingknowe rbt EB- lane closure Direction: E | SRWR: 3542489,3542468,3542490 Location: A75 Dancingknowe rbt EB- lane closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43662 18/03/2024
SW/2024/43663 | A75 | A75 Dancingknowe rbt - lane closure Direction: E | SRWR: 3542468 Location: A75 Dancingknowe rbt - lane closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43663 18/03/2024
SW/2024/43664 | A75 | A75 Brownrigg rbt WB- lane closure Direction: W | SRWR: 3542498, 3542501,3542504 Location: A75 Brownrigg rbt WB- lane closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43664 18/03/2024
SW/2024/43665 | A75 | A75 Brownrigg rbt EB- lane closure Direction: E | SRWR: 3542498,3542501,3542504 Location: A75 Brownrigg rbt EB- lane closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43665 18/03/2024
SW/2024/43666 | A75 | A75 Brownrigg rbt - lane closure Direction: E | SRWR: 3542504 Location: A75 Brownrigg rbt - lane closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43666 18/03/2024
SW/2024/43667 | A75 | A75 Bloomfield rbt WB- lane closure Direction: W | SRWR: 3542514 Location: A75 Bloomfield rbt WB- lane closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43667 18/03/2024
SW/2024/43668 | A75 | A75 Bloomfield rbt EB- lane closure Direction: E | SRWR: 3542517 Location: A75 Bloomfield rbt EB- lane closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43668 18/03/2024
SW/2024/43670 | A75 | A75 Bloomfield rbt - lane closure Direction: S | SRWR: 3542525 Location: A75 Bloomfield rbt - lane closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43670 18/03/2024
SW/2024/43672 | A75 | A75 Cuckoo Bridge, Dumfries W/B - LANE CLOSURE Direction: W | SRWR: 3542680 Location: A75 Cuckoo Bridge, Dumfries W/B - LANE CLOSURE Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43672 18/03/2024
SW/2024/43673 | A75 | A75 Cuckoo Bridge, Dumfries E/B - LANE CLOSURE Direction: E | SRWR: 3542686 Location: A75 Cuckoo Bridge, Dumfries E/B - LANE CLOSURE Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43673 18/03/2024
SW/2024/43674 | A75 | A75 Cuckoo Bridge, Glasgow Road Dumfries S/B - LANE CLOSURE Direction: S | SRWR: 3542730 Location: A75 Cuckoo Bridge, Glasgow Road Dumfries S/B - LANE CLOSURE Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43674 18/03/2024
SW/2024/43675 | A75 | A75 Cuckoo Bridge Roundabout- LANE CLOSURE Direction: S | SRWR: 3542747 Location: A75 Cuckoo Bridge Roundabout- LANE CLOSURE Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43675 18/03/2024
SW/2024/43677 | A75 | A75 New Cargenbridge Roundabout, Dumfries W/B- lane closure Direction: W | SRWR: 3542797 Location: A75 New Cargenbridge Roundabout, Dumfries W/B- lane closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43677 18/03/2024
SW/2024/43678 | A75 | A75 New Cargenbridge Roundabout, Dumfries E/B - lane closure Direction: E | SRWR: 3542808 Location: A75 New Cargenbridge Roundabout, Dumfries E/B - lane closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43678 18/03/2024
SW/2024/43679 | A75 | A75 New Cargenbridge Roundabout, Dumfries - lane closure Direction: S | SRWR: 3542816 Location: A75 New Cargenbridge Roundabout, Dumfries - lane closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43679 18/03/2024
SW/2024/43680 | A75 | A75 Garroch Loaning Rbt WB Lane Closure Direction: W | SRWR: 3542872 Location: A75 Garroch Loaning Rbt WB Lane Closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43680 18/03/2024
SW/2024/43681 | A75 | A75 Garroch Loaning Rbt EB - Lane Closure Direction: E | SRWR: 3542872 Location: A75 Garroch Loaning Rbt EB - Lane Closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43681 18/03/2024
SW/2024/43682 | A75 | A75 Garroch Loaning Rbt - Lane Closure Direction: S | SRWR: 3542872 Location: A75 Garroch Loaning Rbt - Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 19:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/43682 18/03/2024
SW/2024/43831 | A75 | A75 Auchenreoch Loch, Springholm WB TTL's Direction: W | SRWR: 3540671,3540675 Location: A75 Auchenreoch Loch, Springholm WB TTL's Direction: W Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Class 1 | Landscape Maintenance - Amey (Primary) Landscape Maintenance - LJX Tree Surgeons (Secondary) | 2024-03-18 08:00 | 2024-03-29 17:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43831 18/03/2024
SW/2024/43832 | A75 | A75 Auchenreoch Loch, Springholm EB TTL's Direction: E | SRWR: 3540671,3540675 Location: A75 Auchenreoch Loch, Springholm EB TTL's Direction: E Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Class 1 | Landscape Maintenance - Amey (Primary) Landscape Maintenance - LJX Tree Surgeons (Secondary) | 2024-03-18 08:00 | 2024-03-29 17:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43832 18/03/2024
SW/2024/43870 | A75 | A75 Glenluce Bypass WB TTL's Direction: W | SRWR: 3543645 Location: A75 Glenluce Bypass WB TTL's Direction: W Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Pavement Surveys - Amey (Primary) Pavement Surveys - Land & Mineral Survey Services Ltd (Secondary) | 2024-03-23 19:00 | 2024-03-27 06:00 | 2024-03-18 | [5 empty] | X | X | 3 | SW/2024/43870 18/03/2024
SW/2024/43871 | A75 | A75 Glenluce Bypass EB TTL's Direction: E | SRWR: 3543645 Location: A75 Glenluce Bypass EB TTL's Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Pavement Surveys - Amey (Primary) Pavement Surveys - Land & Mineral Survey Services Ltd (Secondary) | 2024-03-23 19:00 | 2024-03-27 06:00 | 2024-03-18 | [5 empty] | X | X | 3 | SW/2024/43871 18/03/2024
SW/2024/43872 | A75 | A75 Hightae to Rhonehouse WB TTL's Direction: W | SRWR: 3540687,3540691 Location: A75 Hightae to Rhonehouse WB TTL's Direction: W Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Drainage Works - Amey (Primary) Drainage Works - Underground Inspections Service (Secondary) | 2024-03-18 08:00 | 2024-03-19 17:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43872 18/03/2024
SW/2024/43873 | A75 | A75 Hightae to Rhonehouse EB TTL's Direction: E | SRWR: 3540687,3540691 Location: A75 Hightae to Rhonehouse EB TTL's Direction: E Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Drainage Works - Amey (Primary) Drainage Works - Underground Inspections Service (Secondary) | 2024-03-18 08:00 | 2024-03-19 17:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43873 18/03/2024
SW/2024/43992 | A75 | A75 NB from B797 Jct Mennock to Jct with B740 Crawick - Diversion Route Direction: N | SRWR: 3537285 Location: A75 NB from B797 Jct Mennock to Jct with B740 Crawick - Diversion Route Direction: N Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Sunbelt Rentals | Road Part of a Diversion Route - Sunbelt Rentals (Secondary) Road Part of a Diversion Route - Dumfries and Galloway Council (Primary) | 2024-03-18 07:00 | 2024-03-29 19:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/43992 18/03/2024
SW/2024/43993 | A75 | A75 SB from B797 Jct Mennock to Jct with B740 Crawick - Diversion Route Direction: S | SRWR: 3537285 Location: A75 SB from B797 Jct Mennock to Jct with B740 Crawick - Diversion Route Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Sunbelt Rentals | Road Part of a Diversion Route - Sunbelt Rentals (Secondary) Road Part of a Diversion Route - Dumfries and Galloway Council (Primary) | 2024-03-18 07:00 | 2024-03-29 19:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/43993 18/03/2024
SW/2024/43994 | A75 | A75 Dunragit to Planting end WB TTL's Direction: W | SRWR: 3541716, 3541721 Location: A75 Dunragit to Planting end WB TTL's Direction: W Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Secondary) | 2024-03-18 06:00 | 2024-03-22 18:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43994 18/03/2024
SW/2024/43995 | A75 | A75 Dunragit to Planting end EB TTL's Direction: E | SRWR: 3541716, 3541721 Location: A75 Dunragit to Planting end EB TTL's Direction: E Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Secondary) | 2024-03-18 06:00 | 2024-03-22 18:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43995 18/03/2024
SW/2024/43996 | A75 | A75 Dunragit WB lane closures Direction: W | SRWR: 3541725 Location: A75 Dunragit WB lane closures Direction: W Delay: Slight Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Primary) | 2024-03-18 06:00 | 2024-03-22 18:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43996 18/03/2024
SW/2024/43997 | A75 | A75 Dunragit EB lane closures Direction: E | SRWR: 3541725 Location: A75 Dunragit EB lane closures Direction: E Delay: Slight Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Primary) | 2024-03-18 06:00 | 2024-03-22 18:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43997 18/03/2024
SW/2024/44057 | A75 | A75 Cairntop Dual WB TTL's Direction: W | SRWR: 3542825 Location: A75 Cairntop Dual WB TTL's Direction: W Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Trial hole investigation - Amey (Primary) | 2024-03-23 08:00 | 2024-03-24 17:00 | 2024-03-18 | [5 empty] | X | X | 2 | SW/2024/44057 18/03/2024
SW/2024/44058 | A75 | A75 Carintop Dual EB TTL's Direction: E | SRWR: 3542825 Location: A75 Carintop Dual EB TTL's Direction: E Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Trial hole investigation - Amey (Primary) | 2024-03-23 08:00 | 2024-03-24 17:00 | 2024-03-18 | [5 empty] | X | X | 2 | SW/2024/44058 18/03/2024
SW/2024/44194 | A75 | A75 Glenluce to Gretna - Verge works Direction: E | SRWR: Location: A75 Glenluce to Gretna - Verge works Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Sunbelt Rentals | Third Party Works - Sunbelt Rentals (Secondary) Third Party Works - Dumfries and Galloway Council (Primary) | 2024-03-18 08:30 | 2024-03-26 15:30 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/44194 18/03/2024
SW/2024/42726 | A76 | A76 SB Between Bellfield Interchange and Crosshands Rbt - Diversion Signage Direction: S | SRWR: 3489549 Location: A76 SB Between Bellfield Interchange and Crosshands Rbt - Diversion Signage Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Apex Traffic Management | Road Part of a Diversion Route - Scottish Power (Primary) Road Part of a Diversion Route - Apex Traffic Management (Secondary) | 2024-03-11 08:00 | 2024-04-07 17:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42726 18/03/2024
SW/2024/42727 | A76 | A76 NB Between Bellfield Interchange and Crosshands Rbt - Diversion Signage Direction: N | SRWR: 3489549 Location: A76 NB Between Bellfield Interchange and Crosshands Rbt - Diversion Signage Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Apex Traffic Management | Road Part of a Diversion Route - Scottish Power (Primary) Road Part of a Diversion Route - Apex Traffic Management (Secondary) | 2024-03-11 08:00 | 2024-04-07 17:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42727 18/03/2024
SW/2024/42742 | A76 | A76 Mansfield to South of New Cumnock - Diversion Signage Direction: S | SRWR: Location: A76 Mansfield to South of New Cumnock - Diversion Signage Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Glenmavis Traffic Management | Road Part of a Diversion Route - Ayrshire Roads Alliance (Primary) | 2024-03-04 08:00 | 2024-03-24 18:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42742 18/03/2024
SW/2024/42743 | A76 | A76 Mansfield to South of New Cumnock - Diversion Signage Direction: N | SRWR: Location: A76 Mansfield to South of New Cumnock - Diversion Signage Direction: N Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Glenmavis Traffic Management | Road Part of a Diversion Route - Ayrshire Roads Alliance (Primary) | 2024-03-04 08:00 | 2024-03-24 18:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42743 18/03/2024
SW/2024/43147 | A76 | A76 NB Barburgh Mill Blackwood - TTLS Direction: N | SRWR: 3526627 Location: A76 NB Barburgh Mill Blackwood - TTLS Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Inspections - Amey (Primary) Inspections - Apex Traffic Management (Primary) Inspections - L & M Surveys (Primary) | 2024-03-20 09:00 | 2024-03-20 17:00 | 2024-03-18 |  |  | X |  |  |  |  | 1 | SW/2024/43147 18/03/2024
SW/2024/43148 | A76 | A76 SB Barburgh Mill Blackwood - TTLS Direction: S | SRWR: 3526627 Location: A76 SB Barburgh Mill Blackwood - TTLS Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Inspections - Amey (Primary) Inspections - Apex Traffic Management (Primary) Inspections - L & M Surveys (Primary) | 2024-03-20 09:00 | 2024-03-20 17:00 | 2024-03-18 |  |  | X |  |  |  |  | 1 | SW/2024/43148 18/03/2024
SW/2024/43348 | A76 | A76 KIlmarnock - Cumnock SB- Verge Works Direction: S | SRWR: Mobile Short Duraration Location: A76 KIlmarnock - Cumnock SB- Verge Works Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - East Ayrshire Council | Third Party Works - East Ayrshire Council (Primary) | 2024-02-26 09:30 | 2024-03-29 15:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/43348 18/03/2024
SW/2024/43349 | A76 | A76 Cumnock - Kilmarnock NB Verge Works Direction: N | SRWR: Mobile Short Duraration Location: A76 Cumnock - Kilmarnock NB Verge Works Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - East Ayrshire Council | Third Party Works - East Ayrshire Council (Primary) | 2024-02-26 09:30 | 2024-03-29 15:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/43349 18/03/2024
SW/2024/43855 | A76 | A76 Kilmarnock Road Crosshands SB - TTL Direction: S | SRWR: 3542030 Location: A76 Kilmarnock Road Crosshands SB - TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/43855 18/03/2024
SW/2024/43856 | A76 | A76 Kilmarnock Road Crosshands NB - TTL Direction: N | SRWR: Location: A76 Kilmarnock Road Crosshands NB - TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/43856 18/03/2024
SW/2024/43857 | A76 | A76 SB Between New Cumnock & Kirkconnel - TTL Direction: S | SRWR: 3542243 Location: A76 SB Between New Cumnock & Kirkconnel - TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Sign Installation/Repairs - Amey (Primary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/43857 18/03/2024
SW/2024/43858 | A76 | A76 NB Between New Cumnock & Kirkconnel - TTL Direction: N | SRWR: 3542243 Location: A76 NB Between New Cumnock & Kirkconnel - TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Sign Installation/Repairs - Amey (Primary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/43858 18/03/2024
SW/2024/43985 | A76 | A76 Auldgirth to Trigony NB Stop/Go Direction: N | SRWR: 3542010 3542011 Location: A76 Auldgirth to Trigony NB Stop/Go Direction: N Delay: Slight Delay/At All Times Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Apex Traffic Management | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Secondary) | 2024-03-18 07:00 | 2024-03-20 17:00 | 2024-03-18 | X | X | X |  |  |  |  | 3 | SW/2024/43985 18/03/2024
SW/2024/43986 | A76 | A76 Auldgirth to Trigony SB Stop/Go Direction: N | SRWR: 3542010 3542011 Location: A76 Auldgirth to Trigony SB Stop/Go Direction: N Delay: Slight Delay/At All Times Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Apex Traffic Management | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Secondary) | 2024-03-18 07:00 | 2024-03-20 17:00 | 2024-03-18 | X | X | X |  |  |  |  | 3 | SW/2024/43986 18/03/2024
SW/2024/43987 | A76 | A76 Ardoch to Mennock NB TTL's Direction: N | SRWR: 3542290 Location: A76 Ardoch to Mennock NB TTL's Direction: N Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Secondary) | 2024-03-21 07:00 | 2024-03-29 17:00 | 2024-03-18 |  |  |  | X | X | X | X | 4 | SW/2024/43987 18/03/2024
SW/2024/43988 | A76 | A76 Ardoch to Mennock SB TTL's Direction: S | SRWR: 3542290 Location: A76 Ardoch to Mennock SB TTL's Direction: S Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Secondary) | 2024-03-21 07:00 | 2024-03-29 17:00 | 2024-03-18 |  |  |  | X | X | X | X | 4 | SW/2024/43988 18/03/2024
SW/2024/43989 | A76 | A76 Mennock to North of Ardoch SB - Lane closures Direction: S | SRWR: 3542300 Location: A76 Mennock to North of Ardoch SB - Lane closures Direction: S Delay: Slight Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Tree Surgery | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Secondary) | 2024-03-21 07:00 | 2024-03-29 17:00 | 2024-03-18 |  |  |  | X | X | X | X | 4 | SW/2024/43989 18/03/2024
SW/2024/43990 | A76 | A76 Mennock to North of Ardoch NB - Lane closures Direction: N | SRWR: 3542300 Location: A76 Mennock to North of Ardoch NB - Lane closures Direction: N Delay: Slight Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Tree Surgery | Filter Drain - Amey (Primary) Filter Drain - AMD Contract Services (Secondary) | 2024-03-21 07:00 | 2024-03-29 17:00 | 2024-03-18 |  |  |  | X | X | X | X | 4 | SW/2024/43990 18/03/2024
SW/2024/44103 | A76 | A76 N\B Thornhill to Carronbridge - Stop Go's Direction: N | SRWR: Short Duration Progressive Stop & Go Location: A76 N\B Thornhill to Carronbridge - Stop Go's Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Touchstone TM | Inspections - Tracsis (Primary) | 2024-03-18 09:30 | 2024-03-26 16:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44103 18/03/2024
SW/2024/44104 | A76 | A76 S\B Carronbridge to Thornhill to- Stop Go's Direction: S | SRWR: Short Duration Progressive Stop & Go Location: A76 S\B Carronbridge to Thornhill to- Stop Go's Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Touchstone TM | Inspections - Tracsis (Primary) | 2024-03-18 09:30 | 2024-03-26 16:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44104 18/03/2024
SW/2024/44106 | A76 | A76 N\B Sanquhar - Kirkconnel - Stop Go's Direction: N | SRWR: Short Duration Progressive Stop & Go Location: A76 N\B Sanquhar - Kirkconnel - Stop Go's Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Touchstone TM | Inspections - Tracsis (Primary) | 2024-03-18 09:30 | 2024-03-26 16:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44106 18/03/2024
SW/2024/44107 | A76 | A76 S\B Kirkconnel to Sanquhar to- Stop Go's Direction: S | SRWR: Short Duration Progressive Stop & Go Location: A76 S\B Kirkconnel to Sanquhar to- Stop Go's Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Touchstone TM | Inspections - Tracsis (Primary) | 2024-03-18 09:30 | 2024-03-26 16:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44107 18/03/2024
SW/2024/44151 | A76 | A76 SB at Netherthird - TTLs Direction: S | SRWR: 3544166 Location: A76 SB at Netherthird - TTLs Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - HBS | Barrier Repair - Amey (Primary) Barrier Repair - HBS (Secondary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/44151 18/03/2024
SW/2024/44152 | A76 | A76 NB after Carronbridge - TTLs Direction: N | SRWR: 3544199 Location: A76 NB after Carronbridge - TTLs Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - HBS | Barrier Repair - Amey (Primary) Barrier Repair - Class 1 (Secondary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/44152 18/03/2024
SW/2024/44197 | A76 | A76 SB at Pathhead New Cumnock - Give and Take Direction: S | SRWR: 3543066 Location: A76 SB at Pathhead New Cumnock - Give and Take Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Give and Take Traffic Control (No Speed Restriction) - Scottish Water | Utility Works - Scottish Water (Primary) | 2024-03-12 09:00 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44197 18/03/2024
SW/2024/44198 | A76 | A76 NB at Pathhead New Cumnock - Give and Take Direction: N | SRWR: 3543066 Location: A76 NB at Pathhead New Cumnock - Give and Take Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Give and Take Traffic Control (No Speed Restriction) - Scottish Water | Utility Works - Scottish Water (Primary) | 2024-03-12 09:00 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44198 18/03/2024
SW/2023/41913 | A77 | A77 Carlock Hill TTL's Southbound Direction: S | SRWR: 3496516 Location: A77 Carlock Hill TTL's Southbound Direction: S Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Emergency Works - Amey (Primary) | 2023-12-27 17:00 | 2024-07-19 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/41913 18/03/2024
SW/2023/41914 | A77 | A77 Carlock Hill TTL's Northbound Direction: N | SRWR: 3496516 Location: A77 Carlock Hill TTL's Northbound Direction: N Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Emergency Works - Amey (Primary) | 2023-12-27 17:00 | 2024-07-19 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/41914 18/03/2024
SW/2024/41956 | A77 | A77 Girvan Railway Station NB - TTL Direction: N | SRWR: 3497924 Location: A77 Girvan Railway Station NB - TTL Direction: N Delay: Slight Delay/Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2024-01-03 14:00 | 2024-03-31 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/41956 18/03/2024
SW/2024/41957 | A77 | A77 Girvan Railway Station SB - TTL Direction: S | SRWR: 3497924 Location: A77 Girvan Railway Station SB - TTL Direction: S Delay: Slight Delay/Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2024-01-03 14:00 | 2024-03-31 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/41957 18/03/2024
SW/2024/42145 | A77 | A77 SB ShallochPark Rbt Stranraer A75 London Road Jct Diversion Direction: S | SRWR: 3486523 Location: A77 SB ShallochPark Rbt Stranraer A75 London Road Jct Diversion Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Contraflow Ltd | Road Part of a Diversion Route - Network Rail (Primary) | 2024-03-16 23:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 3 | SW/2024/42145 18/03/2024
SW/2024/42146 | A77 | A77 from A75 London Road Jct to Shalloch Park NB Diversion Direction: N | SRWR: 3486523 Location: A77 from A75 London Road Jct to Shalloch Park NB Diversion Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Contraflow Ltd | Road Part of a Diversion Route - Network Rail (Primary) | 2024-03-16 23:00 | 2024-03-19 09:00 | 2024-03-18 | X | X | [5 empty] | 3 | SW/2024/42146 18/03/2024
SW/2024/42770 | A77 | A77 Bankfield to Holmston NB Road closure Direction: N | SRWR: 3491205 TRO 3525548 Location: A77 Bankfield to Holmston NB Road closure Direction: N Delay: Moderate Delay/Off Peak Hours Diversion: Northbound traffic will leave the A77 at Bankfield Roundabout, taking the first exit onto the A73 Dalmellington Road and continuing onto Castlehill Road, before turning right at the double roundabout onto the A70 Holmston Road and following to Holmston Roundabout to rejoin the A77. | Road Closure (No Speed Restriction) - Apex Traffic Management | Resurfacing - Amey (Primary) Resurfacing - Breedon Aggregates Ltd (Secondary) Resurfacing - CTM Ltd (Secondary) | 2024-03-11 20:00 | 2024-03-24 06:00 | 2024-03-18 | X | X | X | X | X | X | X | 12 | SW/2024/42770 18/03/2024
SW/2024/42771 | A77 | A77 Bankfield to Holmston SB Road closure Direction: S | SRWR: 3491205 TRO 3525548 Location: A77 Bankfield to Holmston SB Road closure Direction: S Delay: Moderate Delay/Off Peak Hours Diversion: Southbound traffic will leave the A77 at Holmston Roundabout then turn left onto Hillfoot Road, following to the roundabout to take the first exit onto the A73 Dalmellington Road and rejoining the A77 at Bankfield Roundabout. | Road Closure (No Speed Restriction) - Apex Traffic Management | Resurfacing - Amey (Primary) Resurfacing - Breedon Aggregates Ltd (Secondary) Resurfacing - CTM Ltd (Secondary) | 2024-03-11 20:00 | 2024-03-24 06:00 | 2024-03-18 | X | X | X | X | X | X | X | 12 | SW/2024/42771 18/03/2024
SW/2024/42772 | A77 | A77 Bankfield Rbt to Holmston Rbt NB lane closure Direction: N | SRWR: 3525562 Location: A77 Bankfield Rbt to Holmston Rbt NB lane closure Direction: N Delay: Little or No Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Resurfacing - Amey (Primary) Resurfacing - Breedon Aggregates Ltd (Secondary) Resurfacing - CTM Ltd (Secondary) | 2024-03-12 06:00 | 2024-03-22 20:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/42772 18/03/2024
SW/2024/42773 | A77 | A77 Bankfield Rbt to Holmston Rbt SB lane closure Direction: S | SRWR: 3525562 Location: A77 Bankfield Rbt to Holmston Rbt SB lane closure Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Resurfacing - Amey (Primary) Resurfacing - Breedon Aggregates Ltd (Secondary) Resurfacing - CTM Ltd (Secondary) | 2024-03-12 06:00 | 2024-03-22 20:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/42773 18/03/2024
SW/2024/42774 | A77 | A77 Bankfield Rbt Lane Closure Direction: N | SRWR: 3491205 Location: A77 Bankfield Rbt Lane Closure Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Resurfacing - Amey (Primary) Resurfacing - Breedon Aggregates Ltd (Secondary) Resurfacing - CTM Ltd (Secondary) | 2024-03-11 20:00 | 2024-03-23 06:00 | 2024-03-18 | X | X | X | X | X | X |  | 10 | SW/2024/42774 18/03/2024
SW/2024/42775 | A77 | A77 Holmston Rbt Lane Closure Direction: N | SRWR: 3491205 Location: A77 Holmston Rbt Lane Closure Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Resurfacing - Amey (Primary) Resurfacing - Breedon Aggregates Ltd (Secondary) Resurfacing - CTM Ltd (Secondary) | 2024-03-11 20:00 | 2024-03-23 06:00 | 2024-03-18 | X | X | X | X | X | X |  | 10 | SW/2024/42775 18/03/2024
SW/2024/43082 | A77 | A77 Bridgemill Girvan NB- TTL Direction: N | SRWR: 3524374 Location: A77 Bridgemill Girvan NB- TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2024-02-14 12:00 | 2024-03-25 20:00 | 2024-03-18 | X | X | X | X | X | X | X | 8 | SW/2024/43082 18/03/2024
SW/2024/43083 | A77 | A77 Bridgemill Girvan SB TTL Direction: S | SRWR: 3524374 Location: A77 Bridgemill Girvan SB TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2024-02-14 12:00 | 2024-03-25 20:00 | 2024-03-18 | X | X | X | X | X | X | X | 8 | SW/2024/43083 18/03/2024
SW/2024/43145 | A77 | A77 Glengall to Bankfield Rbt NB - TTLs Direction: N | SRWR: 3536798 Location: A77 Glengall to Bankfield Rbt NB - TTLs Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Third Party Works - Amey (Primary) Third Party Works - Apex Traffic Management (Primary) Third Party Works - L & M Surveys (Primary) | 2024-03-21 09:00 | 2024-03-21 17:00 | 2024-03-18 |  |  |  | X |  |  |  | 1 | SW/2024/43145 18/03/2024
SW/2024/43146 | A77 | A77 Glengall to Bankfield Rbt SB - TTLs Direction: S | SRWR: 3536798 Location: A77 Glengall to Bankfield Rbt SB - TTLs Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Apex Traffic Management | Third Party Works - Amey (Primary) Third Party Works - Apex Traffic Management (Primary) Third Party Works - L & M Surveys (Primary) | 2024-03-21 09:00 | 2024-03-21 17:00 | 2024-03-18 |  |  |  | X |  |  |  | 1 | SW/2024/43146 18/03/2024
SW/2024/43190 | A77 | A77 Meiklewood - Grassyards SB - N/S Lane Closure Direction: S | SRWR: 3528631,3528636 Location: A77 Meiklewood - Grassyards SB - N/S Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Kerbing Works - Drumclog Plant Ltd (Primary) Drainage Works - Drumclog Plant Ltd (Primary) | 2024-03-05 20:00 | 2024-03-23 06:00 | 2024-03-18 | X | X | X | X | X | X |  | 20 | SW/2024/43190 18/03/2024
SW/2024/43191 | A77 | A77 Grassyards SB between the slips- N/S Lane Closure Direction: S | SRWR: 3528650 Location: A77 Grassyards SB between the slips- N/S Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Drainage Works - Drumclog Plant Ltd (Primary) Kerbing Works - Drumclog Plant Ltd (Primary) | 2024-03-11 20:00 | 2024-03-26 06:00 | 2024-03-18 | X | X | X | X | X | X | X | 26 | SW/2024/43191 18/03/2024
SW/2024/43339 | A77 | A77 Kirkoswald Road, Maybole SB - TTLs Direction: S | SRWR: 3508507 Location: A77 Kirkoswald Road, Maybole SB - TTLs Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-18 20:00 | 2024-03-20 06:00 | 2024-03-18 | X | X | X |  |  |  |  | 4 | SW/2024/43339 18/03/2024
SW/2024/43340 | A77 | A77 Kirkoswald Road, Maybole NB - TTLs Direction: N | SRWR: 3508507 Location: A77 Kirkoswald Road, Maybole NB - TTLs Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-18 20:00 | 2024-03-20 06:00 | 2024-03-18 | X | X | X |  |  |  |  | 4 | SW/2024/43340 18/03/2024
SW/2024/43343 | A77 | A77 South of Minishant NB - TTLs Direction: N | SRWR: 3508511 Location: A77 South of Minishant NB - TTLs Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-19 20:00 | 2024-03-21 06:00 | 2024-03-18 |  | X | X | X |  |  |  | 4 | SW/2024/43343 18/03/2024
SW/2024/43344 | A77 | A77 South of Minishant SB - TTLs Direction: S | SRWR: 3508511 Location: A77 South of Minishant SB - TTLs Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-19 20:00 | 2024-03-21 06:00 | 2024-03-18 |  | X | X | X |  |  |  | 4 | SW/2024/43344 18/03/2024
SW/2024/43360 | A77 | A77 Main Road close to Junction with Mure Place SB - TTLS Direction: S | SRWR: 3504200 Location: A77 Main Road close to Junction with Mure Place SB - TTLS Direction: S Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Glenmavis Traffic Management | Utility Works - Glenmavis Traffic Management (Secondary) Utility Works - Scottish Power (Primary) | 2024-03-08 08:00 | 2024-03-22 17:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43360 18/03/2024
SW/2024/43361 | A77 | A77 Main Road close to Junction with Mure Place NB - TTLS Direction: N | SRWR: 3504200 Location: A77 Main Road close to Junction with Mure Place NB - TTLS Direction: N Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Glenmavis Traffic Management | Utility Works - Glenmavis Traffic Management (Secondary) Utility Works - Scottish Power (Primary) | 2024-03-08 08:00 | 2024-03-22 17:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43361 18/03/2024
SW/2024/43859 | A77 | A77 Auchencrosh to Ballantrae NB- TTL Direction: N | SRWR: 3542870 Location: A77 Auchencrosh to Ballantrae NB- TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/43859 18/03/2024
SW/2024/43860 | A77 | A77 Ballantrae to Auchencrosh SB- TTL Direction: S | SRWR: 3542870 Location: A77 Ballantrae to Auchencrosh SB- TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/43860 18/03/2024
SW/2024/43861 | A77 | A77 Bellfield IC off slip SB - Lane closure Direction: S | SRWR: 3543899 Location: A77 Bellfield IC off slip SB - Lane closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43861 18/03/2024
SW/2024/43862 | A77 | A77 Kilmarnock Bypass @ Treeswood Rd Jct SB- Lane closure Direction: S | SRWR: 3543794 Location: A77 Kilmarnock Bypass @ Treeswood Rd Jct SB- Lane closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43862 18/03/2024
SW/2024/43863 | A77 | A77 Kilmarnock Road Symington NB- Lane closure Direction: N | SRWR: 3543901 Location: A77 Kilmarnock Road Symington NB- Lane closure Direction: N Delay: Little or No Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43863 18/03/2024
SW/2024/44064 | A77 | A77 close to junction with U38 North of Kirkoswald SB- TTL Direction: S | SRWR: 3543091 Location: A77 close to junction with U38 North of Kirkoswald SB- TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 09:30 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44064 18/03/2024
SW/2024/44065 | A77 | A77 close to junction with U38 North of Kirkoswald NB- TTL Direction: N | SRWR: 3543091 Location: A77 close to junction with U38 North of Kirkoswald NB- TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 09:30 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44065 18/03/2024
SW/2024/44066 | A77 | A77 Benanne close to junction with C121 from B734 S/B- TTL Direction: S | SRWR: 3543206 Location: A77 Benanne close to junction with C121 from B734 S/B- TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-19 09:30 | 2024-03-19 15:30 | 2024-03-18 |  | X | [5 empty] | 1 | SW/2024/44066 18/03/2024
SW/2024/44067 | A77 | A77 Benanne close to junction with C121 from B734 N/B- TTL Direction: N | SRWR: 3543206 Location: A77 Benanne close to junction with C121 from B734 N/B- TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-19 09:30 | 2024-03-19 15:30 | 2024-03-18 |  | X | [5 empty] | 1 | SW/2024/44067 18/03/2024
SW/2024/44068 | A77 | A77 Main Street Ballantrae SB- TTLs Direction: S | SRWR: 3543525 Location: A77 Main Street Ballantrae SB- TTLs Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Gully/ironwork repairs - Amey (Primary) | 2024-03-20 09:30 | 2024-03-20 15:30 | 2024-03-18 |  |  | X |  |  |  |  | 1 | SW/2024/44068 18/03/2024
SW/2024/44069 | A77 | A77 Main Street Ballantrae NB- TTLs Direction: N | SRWR: 3543525 Location: A77 Main Street Ballantrae NB- TTLs Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Gully/ironwork repairs - Amey (Primary) | 2024-03-20 09:30 | 2024-03-20 15:30 | 2024-03-18 |  |  | X |  |  |  |  | 1 | SW/2024/44069 18/03/2024
SW/2024/44070 | A77 | A77 Girvan Road Turnberry S/B- TTL Direction: S | SRWR: 3543697,3543703 Location: A77 Girvan Road Turnberry S/B- TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Sign Installation/Repairs - Amey (Primary) | 2024-03-21 09:30 | 2024-03-21 15:30 | 2024-03-18 |  |  |  | X |  |  |  | 1 | SW/2024/44070 18/03/2024
SW/2024/44071 | A77 | A77 Girvan Road Turnberry N/B- TTL Direction: N | SRWR: 3543697,3543703 Location: A77 Girvan Road Turnberry N/B- TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Sign Installation/Repairs - Amey (Primary) | 2024-03-21 09:30 | 2024-03-21 15:30 | 2024-03-18 |  |  |  | X |  |  |  | 1 | SW/2024/44071 18/03/2024
SW/2024/44112 | A77 | A77 SB Main Street Ballantrae - TTLs Direction: S | SRWR: 3539376 Location: A77 SB Main Street Ballantrae - TTLs Direction: S Delay: Slight Delay/Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Freeflow Traffic Management | Utility Works - BT (Primary) Utility Works - Freeflow Traffic Management (Secondary) | 2024-03-21 08:00 | 2024-03-23 17:00 | 2024-03-18 |  |  |  | X | X | X |  | 3 | SW/2024/44112 18/03/2024
SW/2024/44113 | A77 | A77 NB Main Street Ballantrae - TTLs Direction: N | SRWR: 3539376 Location: A77 NB Main Street Ballantrae - TTLs Direction: N Delay: Slight Delay/Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Freeflow Traffic Management | Utility Works - BT (Primary) Utility Works - Freeflow Traffic Management (Secondary) | 2024-03-21 08:00 | 2024-03-23 17:00 | 2024-03-18 |  |  |  | X | X | X |  | 3 | SW/2024/44113 18/03/2024
SW/2024/44145 | A77 | A77 Whitletts Roundabout South Ayrshire SB- Lane Closure Direction: S | SRWR: 3544080 Location: A77 Whitletts Roundabout South Ayrshire SB- Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/44145 18/03/2024
SW/2024/44155 | A77 | A77 NB On Approach to Grassyards Junction - Lane closure Direction: N | SRWR: 3544268 Location: A77 NB On Approach to Grassyards Junction - Lane closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - HBS | Barrier Repair - Amey (Primary) Barrier Repair - Class 1 (Secondary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/44155 18/03/2024
SW/2024/44192 | A77 | A77 Cairnryan to A75 Glenluce - Verge works Direction: S | SRWR: Location: A77 Cairnryan to A75 Glenluce - Verge works Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Sunbelt Rentals | Third Party Works - Sunbelt Rentals (Secondary) Third Party Works - Dumfries and Galloway Council (Primary) | 2024-03-18 08:30 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44192 18/03/2024
SW/2024/44193 | A77 | A77 Cairnryan to A75 Glenluce - Verge Works Direction: S | SRWR: Location: A77 Cairnryan to A75 Glenluce - Verge Works Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Sunbelt Rentals | Third Party Works - Sunbelt Rentals (Secondary) Third Party Works - Dumfries and Galloway Council (Primary) | 2024-03-18 08:30 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44193 18/03/2024
SW/2023/39497 | A78 | A78 NB Hunterston Stop & Go Direction: N | SRWR: Mobile Short Duration Progressive Stop & Go Location: A78 NB Hunterston Stop & Go Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2022-09-12 09:30 | 2024-04-12 15:30 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2023/39497 18/03/2024
SW/2023/39498 | A78 | A78 SB Hunterston Stop & Go Direction: S | SRWR: Mobile Short Duration Progressive Stop & Go Location: A78 SB Hunterston Stop & Go Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2022-09-12 09:30 | 2024-04-12 15:30 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2023/39498 18/03/2024
SW/2023/40106 | A78 | A78 Hunterston - Signage Only Direction: N | SRWR: 3445311 Location: A78 Hunterston - Signage Only Direction: N Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (40mph) - Class 1 | Advanced signage/diversion on verge - RJ McLeod (Primary) | 2023-10-02 | 2025-04-30 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/40106 18/03/2024
SW/2023/40107 | A78 | A78 Hunterston - Signage Only Direction: S | SRWR: 3445311 Location: A78 Hunterston - Signage Only Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (40mph) - Class 1 | Advanced signage/diversion on verge - RJ McLeod (Primary) | 2023-10-02 | 2025-04-30 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/40107 18/03/2024
SW/2023/40694 | A78 | A78 Waterside Hotel to Seamill - TTL Direction: S | SRWR: 3411470, 3411468 Location: A78 Waterside Hotel to Seamill - TTL Direction: S Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - W & I Gilbert | Drainage Works - W & I Gilbert (Primary) | 2023-11-06 09:30 | 2024-03-28 16:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/40694 18/03/2024
SW/2024/42226 | A78 | A78 NB Shore Rd, Wemyss Bay - TTLs Direction: N | SRWR: 3433536 Wemyss Bay Road 3480148 Location: A78 NB Shore Rd, Wemyss Bay - TTLs Direction: N Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - W & I Gilbert | Drainage Works - W & I Gilbert (Primary) | 2024-01-23 09:30 | 2024-03-28 16:30 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42226 18/03/2024
SW/2024/42227 | A78 | A78 SB Shore Rd, Wemyss Bay - TTLs Direction: S | SRWR: 3433536 Wemyss Bar Road 3480148 Location: A78 SB Shore Rd, Wemyss Bay - TTLs Direction: S Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - W & I Gilbert | Drainage Works - W & I Gilbert (Primary) | 2024-01-23 09:30 | 2024-03-28 16:30 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42227 18/03/2024
SW/2024/43356 | A78 | A78 NB North of Ardossan - TTLs Direction: N | SRWR: 3521524 Location: A78 NB North of Ardossan - TTLs Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Sunbelt Rentals | Utility Works - Scottish Water (Primary) Utility Works - Sunbelt Rentals (Secondary) | 2024-03-18 09:00 | 2024-03-20 18:00 | 2024-03-18 | X | X | X |  |  |  |  | 3 | SW/2024/43356 18/03/2024
SW/2024/43357 | A78 | A78 SB North of Ardossan - TTLs Direction: S | SRWR: 3521524 Location: A78 SB North of Ardossan - TTLs Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Sunbelt Rentals | Utility Works - Scottish Water (Primary) Utility Works - Sunbelt Rentals (Secondary) | 2024-03-18 09:00 | 2024-03-20 18:00 | 2024-03-18 | X | X | X |  |  |  |  | 3 | SW/2024/43357 18/03/2024
SW/2024/43423 | A78 | A78 NB Eglinton Rd at Montfode Rbt - TTls Direction: N | SRWR: 3531921 Location: A78 NB Eglinton Rd at Montfode Rbt - TTls Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Sunbelt Rentals | Utility Works - Scottish Water (Primary) Utility Works - Sunbelt Rentals (Secondary) | 2024-03-21 09:00 | 2024-03-22 18:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/43423 18/03/2024
SW/2024/43424 | A78 | A78 SB Eglinton Rd at Montfode Rbt - TTls Direction: S | SRWR: 3531921 Location: A78 SB Eglinton Rd at Montfode Rbt - TTls Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Sunbelt Rentals | Utility Works - Scottish Water (Primary) Utility Works - Sunbelt Rentals (Secondary) | 2024-03-21 09:00 | 2024-03-22 18:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/43424 18/03/2024
SW/2024/43430 | A78 | A78 Irvine Road at Junction with East Castle Avenue Largs SB -TTLS Direction: S | SRWR: 3529717 Location: A78 Irvine Road at Junction with East Castle Avenue Largs SB -TTLS Direction: S Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Sunbelt Rentals Ltd | Utility Works - Scottish Water (Primary) Utility Works - WGM Engineering (Secondary) | 2024-03-22 09:00 | 2024-03-22 18:00 | 2024-03-18 |  |  |  |  | X |  |  | 1 | SW/2024/43430 18/03/2024
SW/2024/43431 | A78 | A78 Irvine Road at Junction with East Castle Avenue Largs NB -TTLS Direction: N | SRWR: 3529717 Location: A78 Irvine Road at Junction with East Castle Avenue Largs NB -TTLS Direction: N Delay: Slight Delay/At All Times Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Sunbelt Rentals Ltd | Utility Works - Scottish Water (Primary) Utility Works - WGM Engineering (Secondary) | 2024-03-22 09:00 | 2024-03-22 18:00 | 2024-03-18 |  |  |  |  | X |  |  | 1 | SW/2024/43431 18/03/2024
SW/2024/43523 | A78 | A78 Irvine Rd Largs SB- TTL Direction: S | SRWR: 3535678 Location: A78 Irvine Rd Largs SB- TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43523 18/03/2024
SW/2024/43524 | A78 | A78 Irvine Rd Largs NB- TTL Direction: N | SRWR: 3535678 Location: A78 Irvine Rd Largs NB- TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43524 18/03/2024
SW/2024/43589 | A78 | A78 between the slips at Spey Rd EB - Total closure Direction: E | SRWR: 3541382,3541384 TRO 3541387 Location: A78 between the slips at Spey Rd EB - Total closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: follow diversion - Offslip to Spey Rd - Across the road - Onslip from Spey Rd end | Road Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/43589 18/03/2024
SW/2024/43590 | A78 | A78 between the slips at Spey Rd WB - Total closure Direction: W | SRWR: 3541382,3541384 TRO 3541387 Location: A78 between the slips at Spey Rd WB - Total closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: follow diversion - Offslip to Spey Rd - Across the road - Onslip from Spey Rd end | Road Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/43590 18/03/2024
SW/2024/43654 | A78 | A78 SB Flatterton Rd - Bankfoot Rbt - Total Closure Direction: S | SRWR: 3536767 3536771 TRO 3536773 Location: A78 SB Flatterton Rd - Bankfoot Rbt - Total Closure Direction: S Delay: Slight Delay/Off Peak Hours Diversion: A78 Bullring Rbt - A770 - Re-join A78 SB @ Bankfoot Rbt | Road Closure (No Speed Restriction) - Apex Traffic Management | Lining Works - CTM Ltd (Primary) | 2024-03-13 20:00 | 2024-03-21 06:00 | 2024-03-18 | X | X | X | X |  |  |  | 6 | SW/2024/43654 18/03/2024
SW/2024/43660 | A78 | A78 Gallowgate Street, Largs - Skip Direction: S | SRWR: 3537079 Location: A78 Gallowgate Street, Largs - Skip Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - No T/M | Skip/Scaffold - Clyde Metal Recycling Ltd (Primary) | 2024-03-04 09:30 | 2024-03-31 15:30 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/43660 18/03/2024
SW/2024/43695 | A78 | A78 WB Inverkip Rd Greenock TTL Direction: W | SRWR: 3544094 Location: A78 WB Inverkip Rd Greenock TTL Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43695 18/03/2024
SW/2024/43696 | A78 | A78 EB Inverkip Rd Greenock TTL Direction: E | SRWR: 3544094 Location: A78 EB Inverkip Rd Greenock TTL Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43696 18/03/2024
SW/2024/43762 | A78 | A78 Pennyburn to Monktonhead south- 12C mobile closures Direction: S | SRWR: Location: A78 Pennyburn to Monktonhead south- 12C mobile closures Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Mobile Lane Closures (No Speed Restriction) - Amey | Sweeping - Amey (Primary) | 2024-03-18 09:00 | 2024-03-22 16:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43762 18/03/2024
SW/2024/43763 | A78 | A78 Pennyburn to Monktonhead north- 12C mobile closures Direction: N | SRWR: Location: A78 Pennyburn to Monktonhead north- 12C mobile closures Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Mobile Lane Closures (No Speed Restriction) - Amey | Sweeping - Amey (Primary) | 2024-03-18 09:00 | 2024-03-22 16:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43763 18/03/2024
SW/2024/43809 | A78 | A78 Gallowgate Street, Largs - Skip Direction: S | SRWR: 3538474 Location: A78 Gallowgate Street, Largs - Skip Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - No T/M | Skip/Scaffold - D W Parker Ltd (Primary) | 2024-03-06 09:30 | 2024-03-20 15:30 | 2024-03-18 | X | X | X |  |  |  |  | 3 | SW/2024/43809 18/03/2024
SW/2024/43851 | A78 | A78 Routenburn to Largs SB- TTL Direction: S | SRWR: 3541877,3541882,3541992, 3541998 Location: A78 Routenburn to Largs SB- TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43851 18/03/2024
SW/2024/43852 | A78 | A78 Routenburn to Largs NB- TTL Direction: N | SRWR: 3541877,3541882,3541992, 3541998 Location: A78 Routenburn to Largs NB- TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43852 18/03/2024
SW/2024/43853 | A78 | A78 Pennyburn Rbt NB- Lane Closure Direction: N | SRWR: 3542122, 3542130 Location: A78 Pennyburn Rbt NB- Lane Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43853 18/03/2024
SW/2024/43854 | A78 | A78 Eglinton IC to Warrix IC off slip SB Lane closure Direction: S | SRWR: 3542029 Location: A78 Eglinton IC to Warrix IC off slip SB Lane closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43854 18/03/2024
SW/2024/44076 | A78 | A78 Shore Road Skelmorlie SB- TTL Direction: S | SRWR: 3543677 Location: A78 Shore Road Skelmorlie SB- TTL Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 09:30 | 2024-03-22 15:30 | 2024-03-18 |  |  |  |  | X |  |  | 1 | SW/2024/44076 18/03/2024
SW/2024/44077 | A78 | A78 Shore Road Skelmorlie NB- TTL Direction: N | SRWR: 3543677 Location: A78 Shore Road Skelmorlie NB- TTL Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 09:30 | 2024-03-22 15:30 | 2024-03-18 |  |  |  |  | X |  |  | 1 | SW/2024/44077 18/03/2024
SW/2024/44093 | A78 | A78 SB Shore Road North of St Philans - TTLs Direction: S | SRWR: 3530273 Location: A78 SB Shore Road North of St Philans - TTLs Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Sunbelt Rentals | Utility Works - BT (Primary) Utility Works - Sunbelt Rentals (Secondary) | 2024-03-21 09:30 | 2024-03-21 15:30 | 2024-03-18 |  |  |  | X |  |  |  | 1 | SW/2024/44093 18/03/2024
SW/2024/44094 | A78 | A78 NB Shore Road North of St Philans - TTLs Direction: N | SRWR: 3530273 Location: A78 NB Shore Road North of St Philans - TTLs Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Portable Traffic Lights (TTLS) (No Speed Restriction) - Sunbelt Rentals | Utility Works - BT (Primary) Utility Works - Sunbelt Rentals (Secondary) | 2024-03-21 09:30 | 2024-03-21 15:30 | 2024-03-18 |  |  |  | X |  |  |  | 1 | SW/2024/44094 18/03/2024
SW/2024/44153 | A78 | A78 SB Rottenburg to Largs - Progressive Stop & Go Direction: S | SRWR: Progressive stop/go only. Location: A78 SB Rottenburg to Largs - Progressive Stop & Go Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - CTM Ltd | Lining Works - CTM Ltd (Primary) | 2024-03-18 09:30 | 2024-03-18 16:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44153 18/03/2024
SW/2024/44154 | A78 | A78 NB Largs to Rottenburg- Progressive Stop & Go Direction: N | SRWR: Progressive stop/go only. Location: A78 NB Largs to Rottenburg- Progressive Stop & Go Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Stop/Go Boards Traffic Control (No Speed Restriction) - CTM Ltd | Lining Works - CTM Ltd (Primary) | 2024-03-18 09:30 | 2024-03-18 16:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44154 18/03/2024
SW/2024/42052 | A8 | A8 W/B Greenock Road Langbank to Woodhall - O/S lane Direction: W | SRWR: 3460119 and 3460104 Location: A8 W/B Greenock Road Langbank to Woodhall - O/S lane Direction: W Delay: Slight Delay/At All Times Diversion: No Diversion | Lane Closure (50mph) - Class 1 | Barrier Repair - HBS (Primary) | 2024-01-23 09:30 | 2024-04-05 15:30 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42052 18/03/2024
SW/2024/42053 | A8 | A8 E/B Greeenock Road Woodhall to Langbank- O/S lane Direction: E | SRWR: 3460119 and 3460104 Location: A8 E/B Greeenock Road Woodhall to Langbank- O/S lane Direction: E Delay: Slight Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Class 1 | Barrier Repair - HBS (Primary) | 2024-01-23 09:30 | 2024-04-05 15:30 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42053 18/03/2024
SW/2024/42500 | A8 | A8 WB Bullring RBt @ A78 SB HIgh Street Greenock - Diversion Direction: W | SRWR: Location: A8 WB Bullring RBt @ A78 SB HIgh Street Greenock - Diversion Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | No Obstruction on Carriageway or Footway (No Speed Restriction) - Class 1 | Road Part of a Diversion Route - Inverclyde Council (Primary) | 2024-02-01 07:00 | 2024-11-01 19:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42500 18/03/2024
SW/2024/43071 | A8 | A8 Woodhall - Newark WB - O/S Lane Closure Direction: E | SRWR: 3530830 Location: A8 Woodhall - Newark WB - O/S Lane Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Gully/ironwork repairs - Drumclog Plant Ltd (Primary) Lining Works - CTM Ltd (Primary) Resurfacing - Aggregate Industries (Primary) | 2024-03-11 22:30 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 9 | SW/2024/43071 18/03/2024
SW/2024/43072 | A8 | A8 Glasgow Rd - Newark WB - Lane Closure Direction: E | SRWR: 3530830 Location: A8 Glasgow Rd - Newark WB - Lane Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Gully/ironwork repairs - Drumclog Plant Ltd (Primary) Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-15 20:00 | 2024-03-18 06:00 | 2024-03-18 | X | [6 empty] | 3 | SW/2024/43072 18/03/2024
SW/2024/43073 | A8 | A8 Greenock Rd WB - 2 Way TTL's Direction: E | SRWR: 3530843 Location: A8 Greenock Rd WB - 2 Way TTL's Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Gully/ironwork repairs - Drumclog Plant Ltd (Primary) Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-15 20:00 | 2024-03-18 06:00 | 2024-03-18 | X | [6 empty] | 3 | SW/2024/43073 18/03/2024
SW/2024/43074 | A8 | A8 Glasgow Rd - Newark EB Total Closure Direction: E | SRWR: 3530848 TRO Location: A8 Glasgow Rd - Newark EB Total Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Road Closure (No Speed Restriction) - Apex Traffic Management | Gully/ironwork repairs - Drumclog Plant Ltd (Primary) Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-15 20:00 | 2024-03-18 06:00 | 2024-03-18 | X | [6 empty] | 3 | SW/2024/43074 18/03/2024
SW/2024/43445 | A8 | A8 Newark - Woodhall Rbt EB- O/S Lane Closure Direction: E | SRWR: 3533719 Location: A8 Newark - Woodhall Rbt EB- O/S Lane Closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Barrier Repair - HBS (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43445 18/03/2024
SW/2024/43490 | A8 | A8 Cartsdyke Roundabout Greenock EB - Lane Closure Direction: E | SRWR: 3534097 (W&P) 3527941 (SW) Location: A8 Cartsdyke Roundabout Greenock EB - Lane Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Touchstone TM Lane Closure (No Speed Restriction) - Sunbelt Rentals | Utility Works - Scottish Water (Primary) Third Party Works - Water and Pipeline Services (Primary) | 2024-03-07 20:00 | 2024-03-22 06:00 | 2024-03-18 |  | X | X | X | X |  |  | 12 | SW/2024/43490 18/03/2024
SW/2024/43491 | A8 | A8 Cartsdyke Roundabout Greenock WB - Lane Closure Direction: E | SRWR: 3534097 (W&P) 3527941 (SW) Location: A8 Cartsdyke Roundabout Greenock WB - Lane Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Touchstone TM Lane Closure (No Speed Restriction) - Sunbelt Rentals | Utility Works - Scottish Water (Primary) Third Party Works - Water and Pipeline Services (Primary) | 2024-03-12 20:00 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 12 | SW/2024/43491 18/03/2024
SW/2024/43703 | A8 | A8 Greenock Road WB Greenock Rd before Comet Rbt - Lane Closure Direction: W | SRWR: 3544183 Location: A8 Greenock Road WB Greenock Rd before Comet Rbt - Lane Closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43703 18/03/2024
SW/2024/43706 | A8 | A8 EB East Hamilton St Lane Closures Direction: E | SRWR: 3543811 Location: A8 EB East Hamilton St Lane Closures Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43706 18/03/2024
SW/2024/43707 | A8 | A8 WB East Hamilton St Lane Closures Direction: W | SRWR: 3543826,3543811 Location: A8 WB East Hamilton St Lane Closures Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43707 18/03/2024
SW/2024/43731 | A8 | A8 Dalrymple Street EB - Lane Closure Direction: E | SRWR: 3539066 Location: A8 Dalrymple Street EB - Lane Closure Direction: E Delay: Slight Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Contraflow Ltd | Third Party Works - Inverclyde Council (Primary) | 2024-03-07 09:30 | 2024-04-18 16:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/43731 18/03/2024
SW/2024/43895 | A8 | A8 Bogston to Ratho Street WB - Lane closures Direction: W | SRWR: 3542025,3542026, 3542028 Location: A8 Bogston to Ratho Street WB - Lane closures Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Pavement Surveys - Atlas - Pavement Survey (Primary) | 2024-03-18 20:00 | 2024-03-21 06:00 | 2024-03-18 | X | X | X | X |  |  |  | 6 | SW/2024/43895 18/03/2024
SW/2024/43896 | A8 | A8 Bogston to Ratho Street EB- Lane Closures Direction: E | SRWR: 3542025,3542026, 3542028 Location: A8 Bogston to Ratho Street EB- Lane Closures Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Pavement Surveys - Atlas - Pavement Survey (Primary) | 2024-03-18 20:00 | 2024-03-21 06:00 | 2024-03-18 | X | X | X | X |  |  |  | 6 | SW/2024/43896 18/03/2024
SW/2024/44147 | A8 | A8 WB Greenock Rd close to Comet Roundabout Lane closures Direction: W | SRWR: 3544283,3544295 Location: A8 WB Greenock Rd close to Comet Roundabout Lane closures Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/44147 18/03/2024
SW/2023/41160 | A82 | A82 NB Stirling Road Prior to Dunbritton Road - Lane Closure Direction: N | SRWR: 3207062 Location: A82 NB Stirling Road Prior to Dunbritton Road - Lane Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Freeflow Traffic Management | Utility Works - BT (Primary) Utility Works - Circet UK (Primary) | 2024-03-18 09:30 | 2024-03-20 15:30 | 2024-03-18 | X | X | X |  |  |  |  | 3 | SW/2023/41160 18/03/2024
SW/2024/42022 | A82 | A82 NB Alexandria Barloan Rbt to Stoneymollan Closure Direction: N | SRWR: 3484679, 3484686, 3484706, 3484711 Location: A82 NB Alexandria Barloan Rbt to Stoneymollan Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: A82 diversion (both directions: A811, A813, Stirling Rd, Diversion for Renton Rd on-slip: Lennox St, Main St, Bank St, North Main St, Luss Rd, A811 | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - West Dunbartonshire Council (Primary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/42022 18/03/2024
SW/2024/42023 | A82 | A82 SB Alexandria Bypass Stoneymollan - Barloan Rbt - Closure Direction: S | SRWR: 3484679, 3484686, 3484706, 3484711 Location: A82 SB Alexandria Bypass Stoneymollan - Barloan Rbt - Closure Direction: S Delay: Slight Delay/Off Peak Hours Diversion: A82 diversion (both directions: A811, A813, Stirling Rd, Diversion for Renton Rd on-slip: Lennox St, Main St, Bank St, North Main St, Luss Rd, A811 | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - West Dunbartonshire Council (Primary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/42023 18/03/2024
SW/2024/42024 | A82 | A82 SB Alexandria Bypass Renton Road Onslip Direction: S | SRWR: 3484679, 3484686, 3484706, 3484711 Location: A82 SB Alexandria Bypass Renton Road Onslip Direction: S Delay: Slight Delay/Off Peak Hours Diversion: A82 diversion (both directions: A811, A813, Stirling Rd, Diversion for Renton Rd on-slip: Lennox St, Main St, Bank St, North Main St, Luss Rd, A811 | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - West Dunbartonshire Council (Primary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/42024 18/03/2024
SW/2024/42025 | A82 | A82 NB Alexandria Bypass Renton Road offlsip - Closure Direction: N | SRWR: 3484679, 3484686, 3484706, 3484711 Location: A82 NB Alexandria Bypass Renton Road offlsip - Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: A82 diversion (both directions: A811, A813, Stirling Rd, Diversion for Renton Rd on-slip: Lennox St, Main St, Bank St, North Main St, Luss Rd, A811 | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - West Dunbartonshire Council (Primary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/42025 18/03/2024
SW/2024/43890 | A82 | A82 Sterling Rd after Barnhill Rd Jct SB - Lane Closure Direction: S | SRWR: 3542009 Location: A82 Sterling Rd after Barnhill Rd Jct SB - Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-19 09:30 | 2024-03-19 15:30 | 2024-03-18 |  | X | [5 empty] | 1 | SW/2024/43890 18/03/2024
SW/2024/43891 | A82 | A82 after Dumbarton Rd Jct SB - Lane Closure Direction: S | SRWR: Location: A82 after Dumbarton Rd Jct SB - Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-19 09:30 | 2024-03-19 15:30 | 2024-03-18 |  | X | [5 empty] | 1 | SW/2024/43891 18/03/2024
SW/2024/43893 | A82 | A82 NB Stoneymollan Rbt Lane Closures Direction: N | SRWR: 3542027 Location: A82 NB Stoneymollan Rbt Lane Closures Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Gully/ironwork repairs - Amey (Primary) | 2024-03-20 09:30 | 2024-03-20 15:30 | 2024-03-18 |  |  | X |  |  |  |  | 1 | SW/2024/43893 18/03/2024
SW/2024/43928 | A82 | A82 Erskine Bridge On Slip W/B - Slip Closure Direction: W | SRWR: 3535111, TRO 3541177 Location: A82 Erskine Bridge On Slip W/B - Slip Closure Direction: W Delay: Slight Delay/At All Times Diversion: A82 westbound to Dunglass Rbt, A82 Eastbound | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - West Dunbartonshire Council (Primary) | 2024-03-24 06:00 | 2024-03-24 11:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43928 18/03/2024
SW/2024/43933 | A82 | A82 Erskine Bridge WB Off Slip - Closure Direction: W | SRWR: 3535098, TRO 3541669 Location: A82 Erskine Bridge WB Off Slip - Closure Direction: W Delay: Slight Delay/At All Times Diversion: via A82 eastbound, Mountblow Rd, A82 Westbound | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - West Dunbartonshire Council (Primary) | 2024-03-23 06:00 | 2024-03-23 11:00 | 2024-03-18 | [5 empty] | X |  | 1 | SW/2024/43933 18/03/2024
SW/2024/43934 | A82 | A82 Erskine Bridge EB On Slip - Slip Closure Direction: E | SRWR: 3535098, TRO 3541669 Location: A82 Erskine Bridge EB On Slip - Slip Closure Direction: E Delay: Slight Delay/At All Times Diversion: via A82 eastbound, Mountblow Rd, A82 Westbound | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - West Dunbartonshire Council (Primary) | 2024-03-23 06:00 | 2024-03-23 11:00 | 2024-03-18 | [5 empty] | X |  | 1 | SW/2024/43934 18/03/2024
SW/2024/44050 | A82 | A82 Stirling Road SB prior to Milton - Lane Closure Direction: S | SRWR: 3543495 Location: A82 Stirling Road SB prior to Milton - Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-20 09:30 | 2024-03-20 15:30 | 2024-03-18 |  |  | X |  |  |  |  | 1 | SW/2024/44050 18/03/2024
SW/2024/44055 | A82 | A82 Great Western Road NB Erskine to Bowling Lane closures Direction: N | SRWR: 3542910 Location: A82 Great Western Road NB Erskine to Bowling Lane closures Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/44055 18/03/2024
SW/2024/44060 | A82 | A82 Great Western Road NB Bowling to Dunglass Lane closures Direction: N | SRWR: 3542965 Location: A82 Great Western Road NB Bowling to Dunglass Lane closures Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/44060 18/03/2024
SW/2024/44061 | A82 | A82 Dumbarton Road SB Dunglass to Bowling Lane closure Direction: S | SRWR: 3542921,3542923,3542929 Location: A82 Dumbarton Road SB Dunglass to Bowling Lane closure Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-20 20:00 | 2024-03-21 06:00 | 2024-03-18 |  |  | X | X |  |  |  | 2 | SW/2024/44061 18/03/2024
SW/2024/44062 | A82 | A82 Great Western Road SB Bowling to Erskine Lane closure Direction: S | SRWR: 3542998 Location: A82 Great Western Road SB Bowling to Erskine Lane closure Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Cyclic Maintenance - Amey (Primary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/44062 18/03/2024
SW/2024/44109 | A82 | A82 N\B Alexandria Bypass @ River Leven - Lane Closure Direction: N | SRWR: 3543902 Location: A82 N\B Alexandria Bypass @ River Leven - Lane Closure Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Glenmavis Traffic Management | Inspections - L & M Surveys (Primary) | 2024-03-18 09:30 | 2024-03-18 16:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44109 18/03/2024
SW/2024/43925 | A898 | A898 Erskine Bridge Off Slip EB - Slip Closure Direction: E | SRWR: 3535111, TRO 3541177 Location: A898 Erskine Bridge Off Slip EB - Slip Closure Direction: E Delay: Slight Delay/At All Times Diversion: A82 westbound to Dunglass Rbt, A82 Eastbound | Road Closure (No Speed Restriction) - Apex Traffic Management | Third Party Works - West Dunbartonshire Council (Primary) | 2024-03-24 06:00 | 2024-03-24 11:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43925 18/03/2024
SW/2024/43825 | Harbourside | Harbourside Rd Inverkip at Junction with A78 E/B - Lane closure Direction: E | SRWR: 3538639 Location: Harbourside Rd Inverkip at Junction with A78 E/B - Lane closure Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Sign Installation/Repairs - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43825 18/03/2024
SW/2024/43826 | Harbourside | Harbourside rd Inverkip at Junction with A78 W/B - road narrowing Direction: W | SRWR: 3538649 Location: Harbourside rd Inverkip at Junction with A78 W/B - road narrowing Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Road Narrowing (Two Way Working) (No Speed Restriction) - Amey | Sign Installation/Repairs - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43826 18/03/2024
SW/2023/41837 | M74 | M74 Jct 7 SB Offslip - Road Narrowing- Lane Closures Direction: S | SRWR: 3494461 Location: M74 Jct 7 SB Offslip - Road Narrowing- Lane Closures Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | Road Narrowing (Two Way Working) (No Speed Restriction) - Apex Traffic Management | Third Party Works - South Lanarkshire Council (Primary) | 2024-01-15 08:00 | 2024-05-08 20:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/41837 18/03/2024
SW/2023/41859 | M74 | M74 Jct 7 NB Onslip - Road Narrowing Direction: N | SRWR: 3494482 Location: M74 Jct 7 NB Onslip - Road Narrowing Direction: N Delay: Little or No Delay/At All Times Diversion: No Diversion | Road Narrowing (Two Way Working) (No Speed Restriction) - Apex Traffic Management | Third Party Works - South Lanarkshire Council (Primary) | 2024-01-15 08:00 | 2024-05-26 20:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/41859 18/03/2024
SW/2024/42765 | M74 | M74 Junction 6 - HS Closure Direction: S | SRWR: 3517958 Location: M74 Junction 6 - HS Closure Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Apex Traffic Management | Structural Repairs - Amey (Primary) | 2024-03-04 00:01 | 2024-04-18 06:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42765 18/03/2024
SW/2024/42781 | M74 | M74 Junction 6 on slip from Hamilton - HS Closure Direction: S | SRWR: 3518060 Location: M74 Junction 6 on slip from Hamilton - HS Closure Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Apex Traffic Management | Structural Repairs - Amey (Primary) | 2024-03-04 00:01 | 2024-04-18 06:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42781 18/03/2024
SW/2024/42782 | M74 | M74 Junction 6 on slip from Motherwell- HS Closure Direction: S | SRWR: 3518062 Location: M74 Junction 6 on slip from Motherwell- HS Closure Direction: S Delay: Little or No Delay/At All Times Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Structural Investigation Services Limited (SIS Ltd) | Structural Repairs - Amey (Primary) | 2024-03-04 00:01 | 2024-04-18 06:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42782 18/03/2024
SW/2024/43388 | M74 | M74 - M8 WB Jct 23 - 24 Secondary Carriageway Link to Main Line M8 Total Closure Direction: W | SRWR: 3531692 TRO 3534910 Location: M74 - M8 WB Jct 23 - 24 Secondary Carriageway Link to Main Line M8 Total Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: Leave M8 Secondary carriageway Jct 23 offslip - Right Dumbreck Rd - Left Paisley Rd West - 1st exit on Rbt to Paisley Rd West - Right Berryknowes Rd - Cardonald Interchange - Return M8 WB Jct 25 onslip | Road Closure (No Speed Restriction) - Apex Traffic Management | Lining Works - CTM Ltd (Primary) Resurfacing - Aggregate Industries (Primary) | 2024-03-20 21:00 | 2024-03-22 06:00 | 2024-03-18 |  |  | X | X | X |  |  | 8 | SW/2024/43388 18/03/2024
SW/2024/43457 | M74 | M74 Jct 1 Link Road To M8 Jct 21 lane closure Direction: N | SRWR: 3535907 Location: M74 Jct 1 Link Road To M8 Jct 21 lane closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Gantry Works - Merson Signs (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43457 18/03/2024
SW/2024/43301 | M74 | M74 Jct 6 NB Mainline - Lane closure Direction: N | SRWR: 3473684 Location: M74 Jct 6 NB Mainline - Lane closure Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Inspections: Structures - STRUCTURAL INVESTIGATION SERVICES LTD (Primary) | 2024-03-13 20:00 | 2024-03-18 06:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/43301 18/03/2024
SW/2024/43302 | M74 | M74 Jct 6 NB off slip to Hamilton- Total Closure Direction: N | SRWR: 3473695 TRO 3533861 Location: M74 Jct 6 NB off slip to Hamilton- Total Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: M74 NB on slip from Motherwell - M74 Jct 5 NB off slip - M74 Jct 5 SB on slip - M74 Jct 6 sb off slip to Hamilton - Diversion end | Road Closure (No Speed Restriction) - Apex Traffic Management | Inspections: Structures - STRUCTURAL INVESTIGATION SERVICES LTD (Primary) | 2024-03-13 20:00 | 2024-03-18 06:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/43302 18/03/2024
SW/2024/43303 | M74 | M74 Jct 6 NB off slip to Motherwell - Totoal Closure Direction: N | SRWR: 3473691 3533862 Location: M74 Jct 6 NB off slip to Motherwell - Totoal Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: M74 NB on slip from Motherwell - M74 Jct 5 NB off slip - M74 Jct 5 SB on slip - M74 Jct 6 sb off slip to Motherwell - Diversion end | Road Closure (No Speed Restriction) - Apex Traffic Management | Inspections: Structures - STRUCTURAL INVESTIGATION SERVICES LTD (Primary) | 2024-03-13 20:00 | 2024-03-18 06:00 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/43303 18/03/2024
SW/2024/43494 | M74 | M74 Jct 7 and Jct 6 NB - Lane Closures Direction: N | SRWR: 3534926 Location: M74 Jct 7 and Jct 6 NB - Lane Closures Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43494 18/03/2024
SW/2024/43505 | M74 | M74 Jct 10 SB - Lane Closure Direction: S | SRWR: 3534928 Location: M74 Jct 10 SB - Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43505 18/03/2024
SW/2024/43506 | M74 | M74 Jct 10 onslip SB - Total Closure Direction: S | SRWR: 3534930 TRO 3534932 Location: M74 Jct 10 onslip SB - Total Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: follow diversion - Carlisle Rd - Wellburn Interchange - Join M74 NB Jct 10 - Continue to Jct 8 NB - Leave M74 at Jct 8 - Canderside Toll - A71 Swinhill Rd - Rejoin M74 SB at Jct 8 onslip end | Road Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 20:00 | 2024-03-19 06:00 | 2024-03-18 | X | X | [5 empty] | 2 | SW/2024/43506 18/03/2024
SW/2024/43507 | M74 | M74 Jct 6 SB Mainline - Lane closure Direction: S | SRWR: 3473714 3473715 Location: M74 Jct 6 SB Mainline - Lane closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Inspections: Structures - STRUCTURAL INVESTIGATION SERVICES LTD (Primary) | 2024-03-18 20:00 | 2024-03-23 06:00 | 2024-03-18 | X | X | X | X | X | X |  | 10 | SW/2024/43507 18/03/2024
SW/2024/43508 | M74 | M74 Jct 6 SB on slip from Motherwell - Total closure Direction: S | SRWR: 3473730 TRO 3534531 Location: M74 Jct 6 SB on slip from Motherwell - Total closure Direction: S Delay: Slight Delay/Off Peak Hours Diversion: Continue on A723 Motherwell Rd - take 5th exit at Rbt - M74 Jct 6 SB on slip from Hamilton - Diversion End | Road Closure (No Speed Restriction) - Apex Traffic Management | Inspections: Structures - STRUCTURAL INVESTIGATION SERVICES LTD (Primary) | 2024-03-16 20:00 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 9 | SW/2024/43508 18/03/2024
SW/2024/43509 | M74 | M74 Jct 6 NB on slip from Motherwell - Total closure Direction: N | SRWR: 3473719 TRO 3534531 Location: M74 Jct 6 NB on slip from Motherwell - Total closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: Continue on A723 Motherwell Rd - take 5th exit at Rbt - M74 Jct 6 NB on slip from Hamilton - Diversion End | Road Closure (No Speed Restriction) - Apex Traffic Management | Inspections: Structures - STRUCTURAL INVESTIGATION SERVICES LTD (Primary) | 2024-03-16 20:00 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 9 | SW/2024/43509 18/03/2024
SW/2024/43512 | M74 | M74 Jct 8 between the slips SB - Total Closure Direction: S | SRWR: 3536787 TRO 3536788 Location: M74 Jct 8 between the slips SB - Total Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: follow diversion - Leave the M74 SB at Jct 8 offslip - Canderside Toll - Rejoin M74 SB at Jct 8 onslip end | Road Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43512 18/03/2024
SW/2024/43517 | M74 | M74 Jct 6 SB on slip from Motherwell - Total Closure Direction: S | SRWR: 3536796 TRO 3536797 Location: M74 Jct 6 SB on slip from Motherwell - Total Closure Direction: S Delay: Slight Delay/Off Peak Hours Diversion: M74 Jct 6 NB on slip from Motherwell - M74 Jct 5 NB off slip - M74 Jct 5 SB on slip - Diversion End | Road Closure (No Speed Restriction) - Apex Traffic Management | Inspections: Structures - STRUCTURAL INVESTIGATION SERVICES LTD (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43517 18/03/2024
SW/2024/43518 | M74 | M74 Jct 6 SB on slip from Hamilton - Total Closure Direction: S | SRWR: 3536799 TRO 3536797 Location: M74 Jct 6 SB on slip from Hamilton - Total Closure Direction: S Delay: Slight Delay/Off Peak Hours Diversion: M74 Jct 6 NB on slip from Hamilton - M74 Jct 5 NB off slip - M74 Jct 5 SB on slip - Diversion End | Road Closure (No Speed Restriction) - Apex Traffic Management | Inspections: Structures - STRUCTURAL INVESTIGATION SERVICES LTD (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/43518 18/03/2024
SW/2024/43827 | M74 | M74 SB Jct 8 On slip Lane Closure Direction: S | SRWR: 3540498 Location: M74 SB Jct 8 On slip Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43827 18/03/2024
SW/2024/44041 | M74 | M74 Jct 10 to Jct 11 SB - Lane Closure Direction: S | SRWR: 3542645 Location: M74 Jct 10 to Jct 11 SB - Lane Closure Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Carriageway Patching - Amey (Primary) | 2024-03-18 09:30 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44041 18/03/2024
SW/2024/44073 | M74 | M74 N\B J12 - 10 - Progressive H/S Direction: N | SRWR: Location: M74 N\B J12 - 10 - Progressive H/S Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Touchstone TM | Inspections - Tracsis (Primary) | 2024-03-17 20:00 | 2024-03-25 06:00 | 2024-03-18 | X | [5 empty] | X | 2 | SW/2024/44073 18/03/2024
SW/2024/44114 | M74 | M74 N/B J8-7 - N/S Lane closure Direction: N | SRWR: 3544733 Location: M74 N/B J8-7 - N/S Lane closure Direction: N Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Glenmavis Traffic Management | Inspections - L & M Surveys (Primary) | 2024-03-21 20:00 | 2024-03-24 06:00 | 2024-03-18 |  |  |  | X | X | X | X | 6 | SW/2024/44114 18/03/2024
SW/2024/44150 | M74 | M74 S\B J3 - J3a Single Lane Running Direction: S | SRWR: 3511362 Location: M74 S\B J3 - J3a Single Lane Running Direction: S Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Single Lane Running (40mph) - CTM Ltd | Lining Works - CTM Ltd (Primary) | 2024-03-21 20:00 | 2024-03-22 06:00 | 2024-03-18 |  |  |  | X | X |  |  | 2 | SW/2024/44150 18/03/2024
SW/2023/41796 | M77 | M77 Junction 1 NB - Road Closure Direction: N | SRWR: 3460152 TRO 3494265 Location: M77 Junction 1 NB - Road Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: M77 Northbound traffic will exit M77 at J1 Dumbreck offslip cross Dumbreck Road and rejoin the M77 at J1 Dumbreck on slip. | Road Closure (No Speed Restriction) - HBS | Barrier Repair - HBS (Primary) | 2024-01-22 20:00 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 9 | SW/2023/41796 18/03/2024
SW/2023/41797 | M77 | M77 Junction 1 NB- Hard Shoulder Running Direction: N | SRWR: 3494267 Location: M77 Junction 1 NB- Hard Shoulder Running Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Single Lane Running (No Speed Restriction) - HBS | Barrier Repair - HBS (Primary) | 2024-01-22 20:00 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 9 | SW/2023/41797 18/03/2024
SW/2023/41798 | M77 | M77 Junction 1 SB - L2 closure Direction: S | SRWR: 3460156 Location: M77 Junction 1 SB - L2 closure Direction: S Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - HBS | Barrier Repair - HBS (Primary) | 2024-01-22 20:00 | 2024-03-22 06:00 | 2024-03-18 | X | X | X | X | X |  |  | 9 | SW/2023/41798 18/03/2024
SW/2023/35519 | M8 | M8 WB Woodside - A804 Phoenix Rd Direction: W | SRWR: 3450421 Location: M8 WB Woodside - A804 Phoenix Rd Direction: W Delay: Moderate Delay/Peak Hours Diversion: Diversion: Local Traffic heading West, directed North on Garscube Rd then South on St Georges Rd. M8 Traffic at Rbt directed South on Garscube Rd to Cowcaddens then West on West Graham St to the new junction at M8 Jct 17 On Loop. | Road Closure (No Speed Restriction) - Apex Traffic Management | Structural Repairs - Amey (Primary) Structural Repairs - Taziker Industrial Ltd (Secondary) Structural Repairs - Apex Traffic Management (Secondary) Structural Repairs - Freyssinet UK (Secondary) | 2023-07-22 | 2025-01-31 11:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/35519 18/03/2024
SW/2023/35520 | M8 | M8 Woodside A804 Phoenix Rd EB Direction: E | SRWR: 3450421 Location: M8 Woodside A804 Phoenix Rd EB Direction: E Delay: Moderate Delay/Peak Hours Diversion: EB/WB M8 traffic and EB local traffic directed North on St Georges Rd then South on Garscube Rd to Garscube Rbt or South on North St to Charing Cross. | Road Closure (No Speed Restriction) - Apex Traffic Management | Structural Repairs - Amey (Primary) Structural Repairs - Taziker Industrial Ltd (Secondary) Structural Repairs - Apex Traffic Management (Secondary) Structural Repairs - Freyssinet UK (Secondary) | 2023-07-22 | 2025-01-31 11:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/35520 18/03/2024
SW/2023/35521 | M8 | M8 Woodside - A804 M8 WB Spur Direction: W | SRWR: 3450423 Location: M8 Woodside - A804 M8 WB Spur Direction: W Delay: Moderate Delay/Peak Hours Diversion: Diversion via West Graham St/ M8 Jct 17 WB Loop | Road Closure (No Speed Restriction) - Apex Traffic Management | Structural Repairs - Amey (Primary) Structural Repairs - Taziker Industrial Ltd (Secondary) Structural Repairs - Apex Traffic Management (Secondary) Structural Repairs - Freyssinet UK (Secondary) | 2023-07-22 | 2025-01-31 11:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/35521 18/03/2024
SW/2023/37052 | M8 | M8 WB JCT 15 On Slip Stirling Rd - Slip Closure Direction: W | SRWR: 2986325 Location: M8 WB JCT 15 On Slip Stirling Rd - Slip Closure Direction: W Delay: Moderate Delay/At All Times Diversion: No Diversion | Road Closure (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2021-03-12 18:00 | 2024-05-16 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/37052 18/03/2024
SW/2023/37053 | M8 | M8 WB JCT 15 - JCT 19 - Lane Closures Direction: W | SRWR: 2972996 Location: M8 WB JCT 15 - JCT 19 - Lane Closures Direction: W Delay: Moderate Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2021-03-12 18:00 | 2024-05-16 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/37053 18/03/2024
SW/2023/37054 | M8 | M8 WB JCT 17 Off Slip Closure Direction: W | SRWR: 2973055 Location: M8 WB JCT 17 Off Slip Closure Direction: W Delay: Moderate Delay/At All Times Diversion: No Diversion | Road Closure (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2021-03-12 18:00 | 2024-05-16 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/37054 18/03/2024
SW/2023/37057 | M8 | M8 EB JCT 17 On Slip - Slip Closure Direction: E | SRWR: 2973091 Location: M8 EB JCT 17 On Slip - Slip Closure Direction: E Delay: Moderate Delay/At All Times Diversion: No Diversion | Road Closure (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2021-03-12 18:00 | 2024-05-16 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/37057 18/03/2024
SW/2023/37058 | M8 | M8 EB JCT 17 to JCT 16 - Lane Closure Direction: E | SRWR: 2973099 Location: M8 EB JCT 17 to JCT 16 - Lane Closure Direction: E Delay: Moderate Delay/At All Times Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Emergency Works - Amey (Primary) | 2021-03-12 18:00 | 2024-05-16 23:59 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2023/37058 18/03/2024
SW/2024/42846 | M8 | M8 J13 to 15 EB - Lane Closure Direction: E | SRWR: 3494716 Location: M8 J13 to 15 EB - Lane Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-21 22:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/42846 18/03/2024
SW/2024/42847 | M8 | M8 J13 to 15 WB - Lane Closure Direction: W | SRWR: 3494714 Location: M8 J13 to 15 WB - Lane Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-21 22:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  | X | X | X |  | 4 | SW/2024/42847 18/03/2024
SW/2024/42853 | M8 | M8 W/B J11-12 N/S Lane closure Direction: W | SRWR: 3460220 Location: M8 W/B J11-12 N/S Lane closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (40mph) - HBS | Barrier Repair - HBS (Primary) | 2024-03-10 20:00 | 2024-04-05 06:00 | 2024-03-18 | X | X | X | X | X |  | X | 10 | SW/2024/42853 18/03/2024
SW/2024/42854 | M8 | M8 W/B J11-12 Single lane running - L3 Direction: W | SRWR: 3460220 Location: M8 W/B J11-12 Single lane running - L3 Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Single Lane Running (40mph) - HBS | Barrier Repair - HBS (Primary) | 2024-03-12 20:00 | 2024-03-26 06:00 | 2024-03-18 | X | X | X | X |  |  |  | 6 | SW/2024/42854 18/03/2024
SW/2024/42855 | M8 | M8 W/B J11 On slip - Closure Direction: W | SRWR: 3520665 TRO 3520670 Location: M8 W/B J11 On slip - Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: Traffic wishing to join M8 at J11 onslip will travel W/B on A8 Edinburgh Road turn right onto A80 Cumbernauld Road and right onto J12 onslip where diversion ends. | Road Closure (40mph) - HBS | Barrier Repair - HBS (Primary) | 2024-03-11 20:00 | 2024-03-26 06:00 | 2024-03-18 | X | X | X | X |  |  |  | 6 | SW/2024/42855 18/03/2024
SW/2024/42865 | M8 | M8 Woodside - EB Jct 18 to Jct 16 Road Closure Direction: E | SRWR: 3531818 3531819 TRO 3533188 Location: M8 Woodside - EB Jct 18 to Jct 16 Road Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: EB Traffic off at Jct 18 (St Georges Rd)/St Georges Rd (NB)/Garscube Rd (SB)/Dobbie's Loan (EB) and back on at Jct 16 (Craighall). | Road Closure (No Speed Restriction) - Apex Traffic Management | Structural Repairs - Amey (Primary) Structural Repairs - Taziker Industrial Ltd (Primary) Structural Repairs - Freyssinet (Primary) | 2024-03-17 22:00 | 2024-05-10 06:00 | 2024-03-18 | X | X | X | X | X |  | X | 10 | SW/2024/42865 18/03/2024
SW/2024/42867 | M8 | M8 Woodside - M8 EB Jct 19 (Anderston) On Slip Closure Direction: E | SRWR: 3531821 TRO 3533524 Location: M8 Woodside - M8 EB Jct 19 (Anderston) On Slip Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: EB Traffic diverted to North St (NB)/St Georges Rd (NB) to meet Main EB diversion at St Georges X. | Road Closure (No Speed Restriction) - Apex Traffic Management | Structural Repairs - Amey (Primary) | 2024-03-17 22:00 | 2024-05-10 06:00 | 2024-03-18 | X | X | X | X | X |  | X | 10 | SW/2024/42867 18/03/2024
SW/2024/42868 | M8 | M8 Woodside - M8 EB Jct 18 (Charing X) On Slip closure Direction: E | SRWR: 3531822 TRO 3533524 Location: M8 Woodside - M8 EB Jct 18 (Charing X) On Slip closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: EB Traffic diverted to St Georges Rd (NB) to meet main diversion att St Georges X | Road Closure (No Speed Restriction) - Apex Traffic Management | Structural Repairs - Amey (Primary) | 2024-03-17 22:00 | 2024-05-10 06:00 | 2024-03-18 | X | X | X | X | X |  | X | 10 | SW/2024/42868 18/03/2024
SW/2024/43737 | M8 | M8 Woodside - Jct 18 (St Georges Rd) Off Slip Closure Direction: E | SRWR: 3540057 TRO 3540058 Location: M8 Woodside - Jct 18 (St Georges Rd) Off Slip Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: Traffic will be diverted Off at EB Jct 19 (Bothwell) and then follow Pitt St NB/St Vincent St WB/North St NB/St Georges Rd NB/Garscube Rd SB/Dobbie's Loan EB and back on again at EB Jct 16 (Craighall). | Road Closure (No Speed Restriction) - Apex Traffic Management | Cyclic Maintenance - Amey (Primary) | 2024-03-19 22:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43737 18/03/2024
SW/2024/43138 | M8 | M8 EB Jct 26 - 24 - Total Closure Direction: E | SRWR: 3531840 3531841 TRO 3536021 Location: M8 EB Jct 26 - 24 - Total Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: Leave at Jct 26 off slip to roundabout – take 1st exit onto A739 to Hillington 2 Roundabout – take 3rd exit onto Renfrew Road, Shieldhall Road and Edmiston Drive to roundabout at Helen Street – take 3rd exit onto Helen Street to Junction 24 at traffic signals – turn left onto slip road to rejoin M8 eastbound. | Road Closure (No Speed Restriction) - Apex Traffic Management | Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-22 20:00 | 2024-03-24 06:00 | 2024-03-18 |  |  |  |  | X | X | X | 8 | SW/2024/43138 18/03/2024
SW/2024/43139 | M8 | M8 EB Jct 26 EB Onslip - Total Closure Direction: E | SRWR: 3531842 TRO 3536021 Location: M8 EB Jct 26 EB Onslip - Total Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: Continue round Rbt take 3rd exit onto A739 to Hillington 2 Roundabout – take 3rd exit onto Renfrew Road, Shieldhall Road and Edmiston Drive to roundabout at Helen Street – take 3rd exit onto Helen Street to Junction 24 at traffic signals – turn left onto slip road to rejoin M8 eastbound. | Road Closure (No Speed Restriction) - Apex Traffic Management | Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-22 20:00 | 2024-03-24 06:00 | 2024-03-18 |  |  |  |  | X | X | X | 8 | SW/2024/43139 18/03/2024
SW/2024/43140 | M8 | M8 EB Jct 25A EB Onslip - Total Closure Direction: E | SRWR: 3531843 TRO 3536036 Location: M8 EB Jct 25A EB Onslip - Total Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: Continue to Kings Inch Rd - Renfrew Road, Shieldhall Road and Edmiston Drive to roundabout at Helen Street – take 3rd exit onto Helen Street to Junction 24 at traffic signals – turn left onto slip road to rejoin M8 eastbound | Road Closure (No Speed Restriction) - Apex Traffic Management | Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-22 20:00 | 2024-03-24 06:00 | 2024-03-18 |  |  |  |  | X | X | X | 8 | SW/2024/43140 18/03/2024
SW/2024/43141 | M8 | M8 EB Jct 25 EB offslip to A739 - Total Closure Direction: E | SRWR: 3531844 TRO 3536205 Location: M8 EB Jct 25 EB offslip to A739 - Total Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: Leave M8 Jct 26 take 1st exit onto A739 to Hillington 2 Roundabout – take 3rd exit onto Renfrew Road, Shieldhall Road take first exit to onslip A739 - End | Road Closure (No Speed Restriction) - Apex Traffic Management | Lining Works - CTM Ltd (Primary) Resurfacing - Aggregate Industries (Primary) | 2024-03-22 20:00 | 2024-03-24 06:00 | 2024-03-18 |  |  |  |  | X | X | X | 8 | SW/2024/43141 18/03/2024
SW/2024/43142 | M8 | M8 A739 - EB Jct 25 Onslip - Total Closure Direction: E | SRWR: 3531845 TRO 3536239 Location: M8 A739 - EB Jct 25 Onslip - Total Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: Traffic brought off onto Langlands Road to roundabout at Shieldhall Road/Langlands Road – take 1st exit to join Shieldhall Rd and Edmiston Drive to roundabout at Helen Street – take 3rd exit onto Helen Street to Junction 24 at traffic signals – turn left onto slip road to rejoin M8 eastbound. | Road Closure (No Speed Restriction) - Apex Traffic Management | Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-22 20:00 | 2024-03-24 06:00 | 2024-03-18 |  |  |  |  | X | X | X | 8 | SW/2024/43142 18/03/2024
SW/2024/43143 | M8 | M8 EB Jct 24 Offslip - Total Closure Direction: E | SRWR: 3531846 TRO 3536021 Location: M8 EB Jct 24 Offslip - Total Closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: Leave at Jct 26 off slip to roundabout – take 1st exit onto A739 to Hillington 2 Roundabout – take 3rd exit onto Renfrew Road, Shieldhall Road and Edmiston Drive to roundabout at Helen Street – take 3rd exit onto Helen Street | Road Closure (No Speed Restriction) - Apex Traffic Management | Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-22 20:00 | 2024-03-24 06:00 | 2024-03-18 |  |  |  |  | X | X | X | 8 | SW/2024/43143 18/03/2024
SW/2024/43184 | M8 | M8 WB Jct 24 - 25 - Total Closure Direction: W | SRWR: 3483124 3531662 TRO 3534892 Location: M8 WB Jct 24 - 25 - Total Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: Leave M8 WB Jct 24 offslip - Left to Helen Street - 2nd exit on Rbt to Paisley Rd West - Right Berryknowes Rd - Cardonald Interchange - Return M8 WB Jct 25 onslip | Road Closure (No Speed Restriction) - Apex Traffic Management | Lining Works - CTM Ltd (Primary) Resurfacing - Aggregate Industries (Primary) | 2024-03-20 21:00 | 2024-03-22 06:00 | 2024-03-18 |  |  | X | X | X |  |  | 8 | SW/2024/43184 18/03/2024
SW/2024/43185 | M8 | M8 WB Jct 24 WB Onslip - Total Closure Direction: W | SRWR: 3531669 TRO 3534892 Location: M8 WB Jct 24 WB Onslip - Total Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: Continue on Helen Street - 2nd exit on Rbt to Paisley Rd West - Right Berryknowes Rd - Cardonald Interchange - Return M8 WB Jct 25 onslip | Road Closure (No Speed Restriction) - Apex Traffic Management | Lining Works - CTM Ltd (Primary) Resurfacing - Aggregate Industries (Primary) | 2024-03-20 21:00 | 2024-03-22 06:00 | 2024-03-18 |  |  | X | X | X |  |  | 8 | SW/2024/43185 18/03/2024
SW/2024/43186 | M8 | M8 WB Jct 25 WB offslip - Total Closure Direction: W | SRWR: 3534906 TRO 3534892 Location: M8 WB Jct 25 WB offslip - Total Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: Leave M8 WB Jct 24 offslip - Left to Helen Street - 2nd exit on Rbt to Paisley Rd West - Right Berryknowes Rd - Cardonald Interchange - Return M8 WB Jct 25 onslip | Road Closure (No Speed Restriction) - Apex Traffic Management | Resurfacing - Aggregate Industries (Primary) Lining Works - CTM Ltd (Primary) | 2024-03-20 21:00 | 2024-03-22 06:00 | 2024-03-18 |  |  | X | X | X |  |  | 8 | SW/2024/43186 18/03/2024
SW/2024/43194 | M8 | M8 Jct 21 On slip - Closure Direction: W | SRWR: 3535887 TRO 3535895 Location: M8 Jct 21 On slip - Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: Diversion via: Carnoustie St, Scotland St, M8 Jct 21 EB On slip, End. | Road Closure (No Speed Restriction) - Apex Traffic Management | Gantry Works - Merson Signs (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43194 18/03/2024
SW/2024/43458 | M8 | M8 (Secondary carriageway) Jct 22 – Jct 23 WB.- Closure Direction: N | SRWR: 3535919 TRO 3535943 Location: M8 (Secondary carriageway) Jct 22 – Jct 23 WB.- Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: M77 SB, M77 SB Jct 1 Off Slip, Dumbreck Rd, Paisley Rd W, Helen St, End | Road Closure (No Speed Restriction) - Apex Traffic Management | Gantry Works - Merson Signs (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43458 18/03/2024
SW/2024/43459 | M8 | M8 WB J23 Off slip Closure Direction: W | SRWR: 3535665 TRO 3535672 Location: M8 WB J23 Off slip Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: M77 SB, M77 SB Jct 1 Off Slip, Drumbreck Rd, End | Road Closure (No Speed Restriction) - Apex Traffic Management | Gantry Works - Merson Signs (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43459 18/03/2024
SW/2024/43460 | M8 | M8 WB J23 Lane 1 & 2 Closure Direction: W | SRWR: 3535686 Location: M8 WB J23 Lane 1 & 2 Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Apex Traffic Management | Gantry Works - Merson Signs (Primary) | 2024-03-19 20:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43460 18/03/2024
SW/2024/43419 | M8 | M8 Westbound Jct 13 Provan to Jct 14 Blochairn - Hard Shoulder Closure Direction: W | SRWR: 3450128 Location: M8 Westbound Jct 13 Provan to Jct 14 Blochairn - Hard Shoulder Closure Direction: W Delay: Little or No Delay/At All Times Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-11 07:00 | 2024-03-22 19:00 | 2024-03-18 | X | X | X | X | X |  |  | 5 | SW/2024/43419 18/03/2024
SW/2024/43573 | M8 | M8 WB Jct 25 off slip to Fifity Pitches - Slip Cosure Direction: W | SRWR: 3491667 TRO 3534997 Location: M8 WB Jct 25 off slip to Fifity Pitches - Slip Cosure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: JCN 25A for Braehead. Turning right onto Kings Inch Drive, right onto Fitty Pitches Road. | Road Closure (No Speed Restriction) - Coneworx Ltd | Third Party Works - Amey Consulting (Primary) Third Party Works - Network Rail (Primary) | 2024-03-19 22:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43573 18/03/2024
SW/2024/43574 | M8 | M8 WB Jct 24 - 25 - Lane Closure Direction: W | SRWR: 3491667 TRO 3534997 Location: M8 WB Jct 24 - 25 - Lane Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Coneworx Ltd | Third Party Works - Amey Consulting (Primary) Third Party Works - Network Rail (Primary) | 2024-03-19 22:00 | 2024-03-20 06:00 | 2024-03-18 |  | X | X |  |  |  |  | 2 | SW/2024/43574 18/03/2024
SW/2024/43644 | M8 | M8 EB Jct 24 Offslip - No Right Turn Direction: E | SRWR: 3495529 TRO 3543573 Location: M8 EB Jct 24 Offslip - No Right Turn Direction: E Delay: Slight Delay/Off Peak Hours Diversion: Junction 24 off slip E/B>Helen Street>Shieldhall Road>Berryknowes Road>Paisley Road West>END. | Road Closure (No Speed Restriction) - Touchstone TM | Third Party Works - Glasgow City Council (Primary) | 2024-03-23 00:01 | 2024-03-29 23:59 | 2024-03-18 | [5 empty] | X | X | 2 | SW/2024/43644 18/03/2024
SW/2024/43645 | M8 | M8 WB Jct 24 Onslip - Closure Direction: W | SRWR: 3495544 TRO 3543579 Location: M8 WB Jct 24 Onslip - Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: M8 Junction 24 W/B>M8 W/B>Junction 25>Berryknowes Road>Paisley Road West>END. | Road Closure (No Speed Restriction) - Touchstone TM | Third Party Works - Glasgow City Council (Primary) | 2024-03-23 00:01 | 2024-03-29 23:59 | 2024-03-18 | [5 empty] | X | X | 2 | SW/2024/43645 18/03/2024
SW/2024/43646 | M8 | M8 WB Jct 24 Offslip - Closure Direction: W | SRWR: 3495538 TRO 3543579 Location: M8 WB Jct 24 Offslip - Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: M8 Junction 24 W/B>M8 W/B>Junction 25>Berryknowes Road>Paisley Road West>END. | Road Closure (No Speed Restriction) - Touchstone TM | Third Party Works - Glasgow City Council (Primary) | 2024-03-23 00:01 | 2024-03-29 23:59 | 2024-03-18 | [5 empty] | X | X | 2 | SW/2024/43646 18/03/2024
SW/2024/43684 | M8 | M8 J13 - J14 Westbound - Lane closure Direction: W | SRWR: 3537515 3537509 Location: M8 J13 - J14 Westbound - Lane closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Class 1 | Trial hole investigation - HBS (Primary) | 2024-03-24 20:00 | 2024-03-26 06:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43684 18/03/2024
SW/2024/43685 | M8 | M8 J14 J13 Eastbound - Lane closure Direction: E | SRWR: 3537524 3537525 Location: M8 J14 J13 Eastbound - Lane closure Direction: E Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Class 1 | Trial hole investigation - HBS (Primary) | 2024-03-24 20:00 | 2024-03-26 06:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/43685 18/03/2024
SW/2024/43845 | M8 | M8 W/B J11-12 H/S closure Direction: W | SRWR: 3538987 3544425 Location: M8 W/B J11-12 H/S closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - HBS | Barrier Repair - HBS (Primary) | 2024-03-19 20:00 | 2024-04-04 06:00 | 2024-03-18 |  | X | X |  |  |  | X | 3 | SW/2024/43845 18/03/2024
SW/2024/43846 | M8 | M8 W/B J11 Offslip Closure Direction: W | SRWR: 3460225 TRO 3538966 3544430 TRO 3544432 Location: M8 W/B J11 Offslip Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: Traffic wishing to exit the M8 at J11 W/B offslip will continue on M8 and exit at J12, turn right onto A80 Cumbernauld road at the top of the slip, then right onto B765 Gartloch Road and at the end of the road turn right onto B765 Avenue End Road, becoming Stepps Road where the diversion ends at M8 J11. | Road Closure (No Speed Restriction) - HBS | Barrier Repair - HBS (Primary) | 2024-03-19 20:00 | 2024-04-04 06:00 | 2024-03-18 |  | X | X |  |  |  | X | 3 | SW/2024/43846 18/03/2024
SW/2024/44083 | M8 | M8 WB Jct 25 - Lane 1 Closure Direction: W | SRWR: 3543425 Location: M8 WB Jct 25 - Lane 1 Closure Direction: W Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Class 1 | Barrier Repair - Amey (Primary) | 2024-03-24 20:00 | 2024-03-25 06:00 | 2024-03-18 | [6 empty] | X | 1 | SW/2024/44083 18/03/2024
SW/2024/44144 | M8 | M8 EB Jct 21 - Lane closures Direction: E | SRWR: 3544708 Location: M8 EB Jct 21 - Lane closures Direction: E Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Sign Installation/Repairs - Amey (Primary) | 2024-03-22 20:00 | 2024-03-23 06:00 | 2024-03-18 |  |  |  |  | X | X |  | 2 | SW/2024/44144 18/03/2024
SW/2024/42265 | M80 | M80 SB Jct 1 to M8 WB Jct 13 Slip Lanes Narrow/HS Closure Direction: W | SRWR: 3491101 Location: M80 SB Jct 1 to M8 WB Jct 13 Slip Lanes Narrow/HS Closure Direction: W Delay: Little or No Delay/Off Peak Hours Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Contraflow Ltd | Ancillary Works - Amey (Primary) | 2024-02-02 06:00 | 2024-07-27 06:00 | 2024-03-18 | X | X | X | X | X | X | X | 7 | SW/2024/42265 18/03/2024
SW/2024/43800 | M80 | M80 NB Jct 1 to 2 Lane Closures Direction: N | SRWR: 3539768 Location: M80 NB Jct 1 to 2 Lane Closures Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Gully/ironwork repairs - Amey (Primary) | 2024-03-18 20:00 | 2024-03-20 06:00 | 2024-03-18 | X | X | X |  |  |  |  | 4 | SW/2024/43800 18/03/2024
SW/2024/43801 | M80 | M80 SB Jct 1 to 2 Lane Closures Direction: N | SRWR: 3539785 Location: M80 SB Jct 1 to 2 Lane Closures Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Lane Closure (No Speed Restriction) - Amey | Gully/ironwork repairs - Amey (Primary) | 2024-03-18 20:00 | 2024-03-20 06:00 | 2024-03-18 | X | X | X |  |  |  |  | 4 | SW/2024/43801 18/03/2024
SW/2024/44199 | M80 | M80 NB jct 1 - 2 - HS Closure Direction: N | SRWR: 3545160 Location: M80 NB jct 1 - 2 - HS Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-18 09:30 | 2024-03-18 15:30 | 2024-03-18 | X | [6 empty] | 1 | SW/2024/44199 18/03/2024
SW/2024/44202 | M80 | M80 NB @ Jct 2 offlsip HS Closure Direction: N | SRWR: 3545177 Location: M80 NB @ Jct 2 offlsip HS Closure Direction: N Delay: Slight Delay/Off Peak Hours Diversion: No Diversion | Hard Shoulder Closure (No Speed Restriction) - Contraflow Ltd | Third Party Works - Amey (Primary) | 2024-03-19 09:30 | 2024-03-19 15:30 | 2024-03-18 |  | X | [5 empty] | 1 | SW/2024/44202 18/03/2024